FLOOD FIGHTING PLAN

2024

FLOOD BUND DIVISION

NAROWAL

IRRIGATION DEPARTMENT

LINK CIRCLE,

LAHORE

IRRIGATION LAHORE ZONE,

LAHORE

LAHORE

I N D E X

FLOOD FIGHTING PLAN 2024

| Chapter | PART-A |  |  | Page No |
| --- | --- | --- | --- | --- |
| 1 | Salient Feature of Division |  |  | 2 |
| 1.1 | Location |  |  | 2 |
| 1.2 | General Description |  |  | 2-3 |
| 1.3 | Administrative Setup |  |  | 4 |
| 2 | Flood Protection and River Training Works |  |  | 5 |
| 2.1 | Design parameter of Training works |  |  | 5-7 |
| 2.2 | Location Map |  |  | 8 |
| 3 | Brief History of Past Flood Events |  |  | 9-15 |
| 4 | Design Data, Historic Peak flood data and previous Five Years Flood Data of Headworks / Barrages and or other control points |  |  | 16 |
| 4.1 | Flood Limits |  |  | 16 |
| 4.2 | Time Lags of Flood |  |  | 16 |
| 4.3 | Highest Floods |  |  | 16 |
| 4.4 | Flood Gauges |  |  | 17 |
| 4.5 | Peak Discharges |  |  | 17-18 |
| 5 | Flood Fighting Strategy |  |  | 19-20 |
| 6 | Flood Damages Restoration Works |  |  | 21-22 |
| 7 | Flood Fighting Watching Arrangements |  |  | 23 |
| 7.1 | Pre Flood Arrangements |  |  | 23 |
| 7.2 | Watching Establishment |  |  | 24 |
| 7.3 | Arrangements at sensitive sites |  |  | 24-25 |
| 7.4 | Watching Material |  |  | 25-26 |
| 7.5 | Arrangement of sounding and probing |  |  | 26 |
| 7.6 | Lighting Arrangement |  |  | 26-27 |
| 7.7 | Ration Arrangements |  |  | 27 |
| 7.8 | POL Arrangement for Vehicle |  |  | 27 |
| 7.9 | Transportation |  |  | 27 |
| 7.10 | Law and Order |  |  | 27 |
| 7.11 | Medical Arrangement for Labour |  |  | 27 |
| 7.12 | Liaison with other Departments |  |  | 27-28 |
| 7.13 | Role of Army |  |  | 29 |
| 7.14 | Duties of Telephone Attendant |  |  | 29 |
| 7.15 | Wireless Arrangements |  |  | 29 |
| 8 | Detail of Encroachment |  |  | 30 |
| 9 | Duty Roster / Flood Fighting Program |  |  | 31-32 |
| 10 | Emergency Telephone Nos. |  |  | 33-34 |
| 11 | Standard Operating Procedure (SOP) for Breaching Section |  |  | 35 |
| 11.1 | History of the Breaching Section |  |  | 35 |
| 11.2 | Location, Design, Quantity and Verity of the Explosive required for detonation |  |  | 35 |
| 11.3 | Arrangement of Explosive and security of Explosive Store |  |  | 35 |
| 11.4 | List of the Security Staff along with detail of their Training etc. |  |  | 35 |
| 11.5 | Detail of Mechanical Means as a Standby Arrangement in case of Detonation Failure. |  |  | 35 |
| 11.6 | Duty roster in case of critical situation |  |  | 35 |
| 11.7 | Breaching committee with their action plan |  |  | 35 |
| 11.8 | List of the villages likely to be inundated in case of breach |  |  | 36 |
| 11.9 | Announcement and detail of evacuation arrangements |  |  | 36 |
| 11.10 | Detail of coordination with civil / army authorities |  |  | 36 |
| 11.11 | Parallel communication arrangement |  |  | 36 |
| 11.12 | Index Plan |  |  | 37 |
| Chapter | PART-B |  |  | 38 |
| 12 | Vulnerable Sites of Flood Bund / Structures |  |  | 38 |
| 12.1 | Apprehended breaches in Flood Bunds / Structures |  |  | 38 |
| 12.2 | Operation of Breaching Sections |  |  | 38 |
| 12.3 | Breaches due to rise of flood water, deterioration of flood bunds. |  |  | 38 |
| 13-A | Emergency Contingency Plan For Vulnerable sites |  |  | 39 |
| 13.1 | Plan Showing Route of Flood Water coming out the breach supported with levels |  |  | 40 |
| 13.2 | Detail of Villages, Abadies likely to be affected and this should also be shown on plan. |  |  | 41 |
| 13.3 | Strategy and action taken, explained in detail this may include |  |  | 41 |
|  | 13.3.1 |  | Arrangements | 41 |
|  | 13.3.2 |  | Establishment of Flood Fighting Camps | 41 |
|  | 13.3.3 |  | Duties of Officers/ Officials at their camp sites | 41-42 |
|  | 13.3.4 |  | Departmental Machinery available | 42 |
|  | 13.3.5 |  | Machinery available from private sources | 42 |
|  | 13.3.6 |  | Flood Fighting Material required | 42-43 |
|  | 13.3.7 |  | Flood Fighting Material available | 42-43 |
| 13.4 | Detail of other infrastructure like electricity, Sui Gas, Telephone Installation, Road network, Other Building, Canal and Drainage Network. |  |  | 44 |
| 13-B | Emergency Contingency Plan For Vulnerable sites |  |  | 55 |
| 13.1 | Plan Showing Route of Flood Water coming out the breach supported with levels |  |  | 46 |
| 13.2 | Detail of Villages, Abadies likely to be affected and this should also be shown on plan. |  |  | 47 |
| 13.3 | Strategy and action taken, explained in detail this may include |  |  | 47 |
|  | 13.3.1 |  | Arrangements | 47 |
|  | 13.3.2 |  | Establishment of Flood Fighting Camps | 47 |
|  | 13.3.3 |  | Duties of Officers/ Officials at their camp sites | 47-48 |
|  | 13.3.4 |  | Departmental Machinery available | 48 |
|  | 13.3.5 |  | Machinery available from private sources | 48 |
|  | 13.3.6 |  | Flood Fighting Material required | 48-49 |
|  | 13.3.7 |  | Flood Fighting Material available | 48-49 |
| 13.4 | Detail of other infrastructure like electricity, Sui Gas, Telephone Installation, Road network, Other Building, Canal and Drainage Network. |  |  | 50 |
| 13-C | Emergency Contingency Plan For Vulnerable sites |  |  | 51 |
| 13.1 | Plan Showing Route of Flood Water coming out the breach supported with levels |  |  | 52 |
| 13.2 | Detail of Villages, Abadies likely to be affected and this should also be shown on plan. |  |  | 53 |
| 13.3 | Strategy and action taken, explained in detail this may include |  |  | 53 |
|  | 13.3.1 |  | Arrangements | 53 |
|  | 13.3.2 |  | Establishment of Flood Fighting Camps | 53 |
|  | 13.3.3 |  | Duties of Officers/ Officials at their camp sites | 53-54 |
|  | 13.3.4 |  | Departmental Machinery available | 54 |
|  | 13.3.5 |  | Machinery available from private sources | 54 |
|  | 13.3.6 |  | Flood Fighting Material required | 54-55 |
|  | 13.3.7 |  | Flood Fighting Material available | 54-55 |
| 13.4 | Detail of other infrastructure like electricity, Sui Gas, Telephone Installation, Road network, Other Building, Canal and Drainage Network. |  |  | 56 |
| 13-D | Emergency Contingency Plan For Vulnerable sites |  |  | 57 |
| 13.1 | Plan Showing Route of Flood Water coming out the breach supported with levels |  |  | 58 |
| 13.2 | Detail of Villages, Abadies likely to be affected and this should also be shown on plan. |  |  | 59 |
| 13.3 | Strategy and action taken, explained in detail this may include |  |  | 59 |
|  | 13.3.1 |  | Arrangements | 59 |
|  | 13.3.2 |  | Establishment of Flood Fighting Camps | 59 |
|  | 13.3.3 |  | Duties of Officers/ Officials at their camp sites | 59-60 |
|  | 13.3.4 |  | Departmental Machinery available | 60 |
|  | 13.3.5 |  | Machinery available from private sources | 60 |
|  | 13.3.6 |  | Flood Fighting Material required | 60-61 |
|  | 13.3.7 |  | Flood Fighting Material available | 60-61 |
| 13.4 | Detail of other infrastructure like electricity, Sui Gas, Telephone Installation, Road network, Other Building, Canal and Drainage Network. |  |  | 62 |
| 13-E | Emergency Contingency Plan For Vulnerable sites |  |  | 63 |
| 13.1 | Plan Showing Route of Flood Water coming out the breach supported with levels |  |  | 64 |
| 13.2 | Detail of Villages, Abadies likely to be affected and this should also be shown on plan. |  |  | 65 |
| 13.3 | Strategy and action taken, explained in detail this may include |  |  | 65 |
|  | 13.3.1 |  | Arrangements | 65 |
|  | 13.3.2 |  | Establishment of Flood Fighting Camps | 65 |
|  | 13.3.3 |  | Duties of Officers/ Officials at their camp sites | 65-66 |
|  | 13.3.4 |  | Departmental Machinery available | 66 |
|  | 13.3.5 |  | Machinery available from private sources | 66 |
|  | 13.3.6 |  | Flood Fighting Material required | 66-67 |
|  | 13.3.7 |  | Flood Fighting Material available | 66-67 |
| 13.4 | Detail of other infrastructure like electricity, Sui Gas, Telephone Installation, Road network, Other Building, Canal and Drainage Network. |  |  | 68 |
| 13-F | Emergency Contingency Plan For Vulnerable sites |  |  | 69 |
| 13.1 | Plan Showing Route of Flood Water coming out the breach supported with levels |  |  | 70 |
| 13.2 | Detail of Villages, Abadies likely to be affected and this should also be shown on plan. |  |  | 71 |
| 13.3 | Strategy and action taken, explained in detail this may include |  |  | 71 |
|  | 13.3.1 | Arrangements |  | 71 |
|  | 13.3.2 | Establishment of Flood Fighting Camps |  | 71 |
|  | 13.3.3 | Duties of Officers/ Officials at their camp sites |  | 71-72 |
|  | 13.3.4 | Departmental Machinery available |  | 72 |
|  | 13.3.5 | Machinery available from private sources |  | 72 |
|  | 13.3.6 | Flood Fighting Material required |  | 72-73 |
|  | 13.3.7 | Flood Fighting Material available |  | 72-73 |
| 13.4 | Detail of other infrastructure like electricity, Sui Gas, Telephone Installation, Road network, Other Building, Canal and Drainage Network. |  |  | 74 |
| 14 | ADDITIONAL INFORMATION ACTION PLAN |  |  | 75 |
| 14.1 | Re-shuffling / recouping plan of reserve stock of stone departmentally |  |  | 75 |
| 14.2 | Detail of inlet and outlet crossing along with closing methodology. |  |  | 75 |
| 14.3 | Deployment of machinery (Medium to high flood) |  |  | 75 |
| 14.4 | Deployment of machinery (High to very high) |  |  | 76 |
| 14.5 | Deployment of machinery (Very High to exceptionally high flood) |  |  | 77 |
| 14.6 | Police deployment plan. |  |  | 78 |
| 14.7 | Detail of synthetic bags with capacity of 500 Kg and 1000 Kg. |  |  | 78 |
| 14.8 | Detail of Polythene sheets of black colour to protect upstream slope against wave action and to control seepage through embankment. |  |  | 79 |
| 15 | Back up Divisions (In case of breach) |  |  | 80 |

PART - A

CHAPTER – 1

SALIENT FEATURE OF FLOOD BUND DIVISION, NAROWAL

1.1	LOCATION

The Flood Bund Division Narowal, Irrigation Department has headquarter at Narowal city Tehsil & District Narowal.

1.2	GENERAL DESCRIPTION

The Flood Bund Division Narowal, with headquarter at Narowal city, started functioning on 10/01/1998 along with its two (2 No's) Sub Divisions i.e Flood Bund Sub Division No -1 Shakargarh with head quarter at Kot Nainan & Sialkot Drainage Sub Division Narowal with headquarter at Narowal to control & monitor the fluvial flood situation in District Narowal

The responsibility of Division is to look after all flood protection works along right side of river Ravi from Kot Nainan (16 Km from Shakargarh in south east direction, where river enters in Pakistan territory) to Marala Ravi Link Canal (MRL Canal) and other flood protection works constructed along tributaries of the River Ravi in Narowal District. The River Ravi originates from the basin of Bangla Hills having 3460 Sq Miles catchment area & then flows through the valley into the state of Chamba. After passing through the hilly region, it enters into Pathan Kot of District Gurdaspur at Chundh & after passing through Gurdaspur District, it enters into Pakistan territory near Kot Nainan in tehsil Shakargrah of District Narowal. It departs Narowal District & enters into District Sheikhupura near village Burj, & then again passes from Amritsar District of India. After running 10 miles in India, the river again re-enters into Pakistan territory near the village Aulia Pur District Sheikhupura.The river flow reaches Shahdara after passing a distance of 114 Km from D/S Jassar Bridge.

###### The River has the following main tributaries, which contribute to its flood in District Narowal.

| Sr. No. | Name of Tributary | Length in Miles | Av Slope 1000 ft | Catchment Area in Sq Miles | Likely Maximum Discharge in Cs) | Out Falling at |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Ujh Nullah | 80 | 31.60 | 675 | 200,000 | River Ravi in Indian |
| 2 | Bein Nullah | 48 | 5.90 | 346 | 128,000 | U/S Jassar Bridge |
| 3 | Basanter Nullah | 45 | 6.40 | 224 | 83,000 | D/S Jassar Bridge |

###### In addition to above tributaries of RiverRavi, the high discharge in Deg Nullah also effects the part area of district NarowalD/S Chahoor and Qila Ahmad Abad.

###### Most of the catchment area of River Ravi & its tributaries fall in the Indian Territory & consequently control points are also with Indian Government. There are many flood protection works on both sides of River Ravi which were constructed by India & Pakistan during the past. Ravi River runs in the form of loops along the international boundary within a series of embankments / river training works. Due to provision of series of river training works by India & Pakistan, the river section has been reduced which has changed its flow behavior from normal to aggressive & consequently causing deep scour & serious damages to the flood protection works.

###### Indian Government always aim to conceal high rain fall which concentrates flood situation in upper catchment area of the river, thereby inflicting heavy damages on Pakistan side. There is no timely receipt of flood warning information from the Indian side & it is usually received when the flood peaks would have already passed from the entry point of the River Ravi near Kot Nainan.

###### This flood fighting plan has been discussed / coordinated with civil / army authorities. Any further suggestions / comments if received from any department will be welcomed and incorporated accordingly.

1.3	ADMINISTRATIVE SETUP

EXECUTIVE ENGINEER

Flood Bund Division, Narowal

SUB DIVISIONAL OFFICER

Sialkot Drainage Sub Division,

Narowal

SUB DIVISIONAL OFFICER

Flood Bund Sub Division # 1,

Shakargarh

SUB ENGINEER

Jassar Section,

HQ at Jassar

SUB ENGINEER

Zafarwal Section,

HQ at RD 83+000

Rayya Bund

SUB ENGINEER

Rayya Section,

HQ at RD 23+000 Pejowal Village

SUB ENGINEER

Chandian Section,

HQ at Narowal

SUB ENGINEER

Survey & Investigation Section,

HQ at KotNainan

SUB ENGINEER

HajipurGujran Section,

HQ at KotNainan

SUB ENGINEER

Jalala Section,

HQ at Jalala village

SUB ENGINEER

BhecoChak Section,

HQ at Bhecochak village

CHAPTER - 2

FLOOD PROTECTION AND RIVER TRAINING WORKS

Unit in Feet

2.1 DESIGN PARAMETERS OF TRAINING WORKS / FLOODEMBANKMENTS.

| Sr.# | Name of Bund / Embankment | Reach (ft) | Length in Miles | Top Width (ft) | Slope W.S/ C.S | Free Board Over HFL | Vulnerable Reach |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Flood Bund Sub Division No.1 Shakargarh |  |  |  |  |  |  |  |
| 1.1 Jalala Section |  |  |  |  |  |  |  |
| 1 | Jalala Flood Protection Bund | 0-26700 | 5.34 | 20 | 1:2 1:2.5 | 5’ (1988) | 13+000 – 18+000 |
| 1.2 Hajipur Gujran Section |  |  |  |  |  |  |  |
| 1 | Hajipur Gujran Bund | 0-37700 | 7.550 | 25 | 1:2 1:3 | 6’ (1985) | Bund is insufficient in height i.e. 6 ft above HFL of 1988. The work “Rehabilitation / Restoration of Hajipur Gujran Flood Bund RD 0+000 to 27+759” in progress at site under NDRMF accordingly |
| 2 | Spur No - 1 of Hajipur Gujran Bund | 0-1250 | 0.250 | 20 | 1:3 1:2 | 6’ (1985) |  |
| 3 | Spur No - 2 of Hajipur Gujran Bund i. Stud No - I ii. Stud No - II | 0-1250 0-450 0-250 | 0.250 | 20 | 1:3 1:2 | 6’ (1985) |  |
| 4 | Spur No - 3 of Hajipur Gujran Bund i. Stud No - III ii. Stud No - IV | 0-160 0-170 0-80 | 0.032 | 20 | 1:2 1:2 | 6’ (1985) |  |
| 5 | Spur No - 4 of Hajipur Gujran Bund | 0-230 | 0.046 | 20 | 1:2 1:2 | 6’ (1985) |  |
| 6 | Spur No - 5 of Hajipur Gujran Bund | 0-1250 | 0.250 | 20 | 1:3 1:2 | 6’ (1985) |  |
| 7 | Spur No - 6 of Hajipur Gujran Bund | 0-3800 | 0.760 | 20 | 1:3 1:2 | 6’ (1985) |  |
| 8 | Spur No - 7 of Hajipur Gujran Bund | 0-1350 | 0.270 | 20 | 1:3 1:2 | 6’ (1985) |  |
| 9 | Spur No - 8 of Hajipur Gujran Bund | 0-360 | 0.720 | 20 | 1:3 1:2 | 6’ (1985) |  |
| 1.3 Bheco Chak Section |  |  |  |  |  |  |  |
| 1 | Bheco Chak Flood Bund | 0-30500 | 5.78 | 20 | 1:3 1:2 | 5’ (1985) |  |
| 2 | Supr No - 1 of Bheco Chak Flood Bund | 0-600 | 1.03 | 20 | 1:3 1:2 | 5’ (1985) |  |
| 3 | Supr No - 2 of Bheco Chak Flood Bund | 0-3350 | 0.71 | 20 | 1:3 1:2 | 5’ (1985) |  |
| 4 | Supr No - 3 of Bheco Chak Flood Bund | 0-4500 | 0.90 | 20 | 1:3 1:2 | 5’ (1985) |  |
| 5 | Supr No - 4 of Bheco Chak Flood Bund | 0-4200 | 0.84 | 20 | 1:3 1:2 | 5’ (1985) |  |
| 6 | Supr No - 5 of Bheco Chak Flood Bund | 0-3650 | 0.73 | 20 | 1:3 1:2 | 5’ (1985) |  |
| 7 | Diversion Bund at Maddo Gole Village | 0-5700 | 1.41 | 20 | 1:3 1:2 | 5’ (1985) |  |
| 1.4 Survey & Investigation Section |  |  |  |  |  |  |  |
| 1 | Tie Flood Bund between Hauipur Gujran & Bheco Chak Bund | 0-16500 | 3.20 | 25 | 1:3 1:2 | 6’ (1988) |  |
| 2 | Guide Spur at Chak Narrah | 0-900 | 0.19 | 20 | 1:3 1:2 | 6’ (1988) |  |
| 3 | Guide Spur at Ferozpur | 0-500 | 0.19 | 20 | 1:3 1:2 | 6’ (1988) |  |
| - Sialkot Drainage Sub Division Narowal |  |  |  |  |  |  |  |
| 2.1 Jassar Section |  |  |  |  |  |  |  |
| 1 | Jassar High way Bund | 0-20000 | 4.00 | 24-28 | 1:3 1:2 | 5’ (1973) |  |
| 2 | Jassar Flood Protection Bund | 0-9300 | 1.86 | 25 | 1:3 1:2 | 6’ (1973) | RD 3+000 |
| 3 | Kakkake Spur | 0-1800 | 0.36 | 20 | 1:3 1:2 | 6’ (1973) | Nose of Spur |
| 4 | J- Head Spur | 0-5200 | 1.04 | 20 | 1:3 1:2 | 6’ (1973) | RD 2.5-4.4 Nose |
| 5 | Right Guide Bund | 0-1400 | 0.78 | 25 | 1:3 1:2 |  |  |
| 6 | Approach Bund | 0-1500 | 0.30 | 20 | 1:3 1:2 |  |  |
| 7 | Railway Spur | 0-800 | 0.16 | 15 | 1:3 1:2 |  |  |
| 8 | Flood Bund Along Basantar Nullah | 0-26400 | 5.00 | 15 | 1:3 1:2 | 5’ (1985) |  |
| 2.2 Chandian Section |  |  |  |  |  |  |  |
| 1 | Chandian Mole Head Spur. including Extension Portion. Mole Head Spur at RD 1+500 Earthen Stud at RD 2+200 Mole Head Spur at RD 2+400 | 0-5850 0-3000 0-1600 0-600 0-600 | 1.77 0.32 0.12 0.12 | 25 | 1:3 1:2 | 5’ (1985) 5’ (2002) | Nose & creek portion |
| 2 | Chandian Dowel Bund Earthen Stud at RD 1+200 Earthen Stud at RD 2+300 Mole Head Spur at RD 3+150 | 0-10500 0-600 0-600 0-600 | 2.1 | 25 | 1:3 1:2 | 5’ (1985) 5’ (2002) | RD 3+000 – 5+000 |
| 2.3 Rayya Section |  |  |  |  |  |  |  |
| 1 | Rayya Flood Bund RD 0+000 - 40+000 | 0-40000 | 8.00 | 20 | 1:3 1:2 | 5’ (1973) |  |
| 2 | Mehdi Dogar Bund RD | 0-7800 | 1.56 | 20 | 1:3 1:2 | 5’ (1973) | Nose of spur |
| 3 | Mehdi Dogar Extension Bund | 0-3300 | 0.66 | 20 | 1:3 1:2 | 5’ (1973) |  |
| 4 | Mehdi Dogar Mole Head Bund | 0-3300 | 0.06 | 20 | 1:3 1:2 | 5’ (1973) |  |
| 5 | Mehdi Dogar Spur | 0-3400 | 0.68 | 20 | 1:3 1:2 | 5’ (1973) |  |
| 6 | D/S Chahoor Bridge to Qila Ahmed Abad | 0-50000 /L | 18.94 | 20 | 1:3 1:2 | 4’ (988) | RD.18-20 |
| 7 | Mole Head Spur at RD.6+000/L | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 8 | Mole Head Spur at RD.7+200/L | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 9 | Mole Head Spur at RD.8+000/L | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 10 | Mole Head Spur at RD.8+500/L | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 11 | Mole Head Spur at RD.9+000/L | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 12 | Mole Head Spur at RD.10+000/L | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 13 | Mole Head Spur at RD.11+000/L | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 14 | Mole Head Spur at RD.12+000/L | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 15 | Mole Head Spur at RD.13+000/L | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 16 | Mole Head Spur at RD.13+5000/L | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 17 | Mole Head Spur at RD.18+500/L | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 18 | Mole Head Spur at RD.18+925/L | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 19 | Mole Head Spur at RD.19+500/L | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 20 | Mole Head Spur at RD.20+000/L | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 21 | Sloppy Stud at RD.22+000/L | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 22 | D/S Chahoor Bridge to Qila Ahmed Abad | 0-50000 /R | 18.94 | 20 | 1:3 1:2 | 4’ (1988) | RD.16-17 |
| 23 | Mole Head Spur at RD.11+000/R | 0-0+420 | 0.084 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 24 | Mole Head Spur at RD.11+500/R | 0-0+100 | 0.02 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 25 | Mole Head Spur at RD.12+500/R | 0-0+300 | 0.06 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 26 | Mole Head Spur at RD.13+000/R | 0-0+150 | 0.03 | 20 | 1:2 1:2 | 4’ (1988) |  |
| 2.5 Zafarwal Section |  |  |  |  |  |  |  |
| 1 | Rayya Flood Bund | 40000-94000 | 10.80 | 20 | 1:3 1:2 | 5’ (1973) | RD 71 - 94 |
| 2 | Zafarwal Spur RD 83+000 | 6500 | 1.20 | 25 | 1:3 1:2 | 5’ (1973) |  |
| 3 | Spur RD 65+000 |  | 1.72 | 25 | 1:3 1:2 | 5’ (1988) | RD 0 – 2 & Nose |
| 4 | Spur RD 75+000 |  | 1.64 | 25 | 1:3 1:2 | 5’ (1973) | Nose of Spur |
| 5 | Spur RD 89+000 |  |  | 25 | 1:3 1:2 | 5’ (1988) |  |

CHAPTER - 3

BRIEF HISTORY OF PAST FLOOD EVENTS

FLOOD DAMAGES 1988 -

During flood season 1988, Jalala flood protection bund was breached in-between between RD 14 ~ 15. Resultantly extensive villages (about 104 No) of Tehsil Shakaegarh, District Narowal were massively flooded. Due to high water head, across at breach site of bund, the damages were devastating. The super flood on 24-25 September 1988, which was to the tune of about 6,50,000 Cs at entry into Pakistan opposite Kot Nainan. The T- Head spur No -2 & Spur No -8 of Hajipur Gujran were totally washed away and all flood bunds in the jurisdiction of this division were badly damaged & sustained heavy launching of apron.

FLOOD DAMAGES 1993 – 1998

During exceptionally high flood of 1993, Spur No – 3 & 4 of Hajipur Gujran flood bund, Chandian Mole Head spur were badly damaged, whereas Jassar J- Head Spur & Diversion Bund at Maddo Gale were partially damaged. The Spur No- 8 of Hajipur Gujran flood bund & tail Mole of Bheco Chak Flood Bund were severely damaged during abnormal flood of 1996. Its restoration works was completed after flood. However, it was again damaged during flood 1997.During flood of 1995-96, apex of horse shoe of river opposite Tie Flood Bund developed further & attached with Tie Flood Bund in reach RD 10+000 – 13+000. The river creek further reached in the toe of Tie Flood Bund during 1997 & finally breached the bund during 1998. Restoration of breached portion, as a Ring bund, has been constructed in a length of 5500’ to control the spill water of the River Ravi.

FLOOD DAMAGES 2005 -

During monsoon 2005, a number of freshets supplies were received in River Ravi &UjhNullah, which threatened the safety of bunds at different locations. Alarming situation occurred on 7/7/2005 at RD 3+500 – 4+500 of Jalala Flood Protection Bund near Ujh Nullah when flow started hitting the bund at right angle.  The erosive action was so rapid that it eroded land strip of 30’ width in the toe of bund within few hours and damaged the water side slope of 60% bund. Immediate protective measures were adopted and the erosion was arrested by evening of 10thJuly. Likewise, with rise off load flows in Ravi River on 8/7/2005, sever erosive action started near tail Mole Bheco Chak Bund at reach RD 29+500 – 30+000. Bhecochak bund at this location plays a vital role in protecting a large number of villages situated behind it. Any breach of bund at this site would have created catastrophic losses.

FLOOD DAMAGES 2014 -

During monsoon of 2014, flood as high as 75000 Cs was observed in Nullah Deg which breached.The bund in upper reaches due to which the flood water entered Tehsil zafarwal of District Narowal. The breach of bund was catastrophic as numerous villages were inundated.

FLOOD DAMAGES 2016 –

During flood season 2016, there were heavy freshets in Nullah Ujh that caused significant erosion. The affected reach was from RD 14 to RD 17 of Jalala Flood Protection Bund. Jalala flood bund has experienced high flows and water level attained was 864 ft above sea level. This flow damaged the noses of all 8 earthen spurs. On the recommendation of the Departmental Expert Committee the nose of spur 01 and 04 were converted into solid stone armored. While strengthening of the damaged noses of six number earthen spurs was carried out by dumping and stacking jute bags filled with sand. This emergent work was stopped midway after flood of 2016.

FLOOD DAMAGES 2017 -

A heavy downpour on 13-07-2017 occurred in the catchment area of Ujh Nullah which resulted in torrential flows.  The water level attained as a result of this flow was 860 ft a.s.l. The reconstructed spurs no 01 and 04 reflected/ acted/ functioned well but the intensive flows affected the earthen spurs no 5, 6, 7 and 8 by damaging their noses partially. On 17-06-2017 even higher torrential flows were observed in Ujh Nullah and as a result of the flow the rise in water level was 861 ft above sea level.  This freshet caused significant damage by completely eroding the earthen spurs no 5, 6,7 and 8. Even the toe of the embankment in reach RD16 to RD 17 started eroding with dominant parallel flow along the bund.

FLOOD DAMAGES 2018 -

A heavy downpour during July of 2018 in the catchment area ofUjh Nullah resulted in high flows. The water level attained as a result of this flow was 861 ft. above sea level. This high water level started eroding the embankment d/s of spur No. 8

FLOOD DAMAGES 2020

Anaveragedownpour during July of 2020 in the catchment area of River Ravi and Nullahs resulted in commonflows in Nullah Ujh, Deg Nullah, Bein Nullah and  River Ravi . The water level attained as a result of this flow was 864.50 ft. above sea level at Ujh Nullah. The Max Discharge passed at Jassar was recorded33000 Cs at Jassar. No any major damages occurred during flood season 2020.

FLOOD DAMAGES 2021

Flood magnitude of 20200 Cusecs at Jassar (Low Flood) passed during Flood season 2021 on 27.07.2021 in River Ravi.No major damages of any kind occurred to any structure of Flood Bund Division Narowal, except Chandian Dowel Bund near Chandian Flood Bund at RD.3+800. The work of Chandian Dowel Bund near Chandian Flood Bund at RD.3+800 has been taken up under M&R works and will be carried.

FLOOD DAMAGES 2022

Floods were received frequently in Nullahs / tributaries of River Ravi due to heavy rainfall in upper catchments of the Nullahs during the flood season 2022. Consequent upon torrential rains, Nullah Deg & Ujh received an exceptionally high flood on 15.08.2022. After passage of the freshets following damages have been reported by the field formation of Flood Bund Division Narowal.

JALALA FLOOD PROTECTION OF UJH NULLAH

An exceptionally High Flood entered in Ujh Nullah opposite RD 2+000 of Jalala flood bund and attained the gauge RL 865.30 on 15.08.2022 at 08.00 PM, endured constant for hours and subsided gradually to normal stage on 16.08.2022.

The exceptional discharge aggravated the damages to spur No.6 at RD 16+750 of Jalala Flood Protection Bund such that the armored rounded head of spur has sharpened / eroded.

DEG NULLAH

Deg nullah is a major flood carrying channel and tributary of river Ravi. An exceptionally high flood of 40650 Cusecs was received in deg nullah on 15.08.2022 resultantly a stud at RD 17+000/R washed away and breach occurred between RD 16+000-17+000/R of Deg Nullah due to presence of a thick jungle on the opposite side. The site was taken up on urgent basis and a loop bund was constructed to base the spill of deg nullah and a stud was constructed at RD 16+500/R of the deg nullah to check the erosive action of high velocity water. Tree launching was also done to control the erosion. Frequent flooding in the nullah also damaged a spur 18+925/L.

BHECO CHAK FLOOD BUND OF RIVER RAVI

Numerous freshets were received in river Ravi during the month of July & August 2022 which heavily engaged the spur No.3 of Bheco Chak Flood Bund and the apron of spur was damaged in length of 240 ft resultantly the pitching was also damaged.  The matter was reported to the higher office and this office was allowed to restore the damage portion of spur No.3 Bheco Chak Flood Bund by using available reserve stock of stone at site as per MIP guidelines under supervision of ADP Consultants. In consequences thereof contractor was engaged according to clause 59-Diii of PPRA rules and the apron of the spur was partially restored before the department ordered to stopped the emergent works and suggested to take up the balance work through competitive bidding.

CHANDIAN DOWEL BUND OF RIVER RAVI

Chandian dowel bund direct hit for the last two years. Expert Committee suggested for construction of spur at RD 3+800 of Chandian Dowel Bund for protection of Chandian Dowel Bund. The spur was partially constructed before a freshet of 63000 cusecs on 16.08.2022. As a result of construction of this spur the river become quite on downstream side and deposited silt on affected area but the river become very aggressive on upstream side and created a sharp loop towards Chandian flood bund upstream of spur RD 3+800 and continuously approaching towards the Chandian Dowel Bund.

FLOOD DAMAGES 2023

Continuous floods were received in Nullahs / tributaries of River Ravi due to heavy rainfall in upper catchments of the Nullahs. Consequent upon torrential rains, Nullah Ujh & Deg received an exceptionally high flood on 09.07.2023 & 19.07.2023. Bein Nullah also received Medium level flooding on 09.07.2023 & 19.07.2023. Resultantly, river Ravi recorded a flood of 61776 Cs on 10.07.2023 and 71010 Cs on 20.07.2023 at Jassar gauging station. River Ravi remained in low flood condition from 20.07.2023 to 30.07.2023 consistently. During passage of the freshets newly constructed interventions were engaged causing some launching of stone but the structures behaved excellently and beside protecting the embankments they diverted the river and nullahs away from the embankments. Launching of apron/damages to other  structures were also observed detail of which is as under:-

- JALALA FLOOD PROTECTION OF UJH NULLAH

An exceptionally High Flood entered in Ujh Nullah opposite RD 2+000 of Jalala flood bund and attained the gauge RL 865.00 on 09.07.2023 at 11.00 AM, endured constant for hours and subsided gradually to normal stage on 12.07.2023.

No damage to any structure was observed but the main creek is currently flowing at the distance of 1500 ft from the embankment in between RD 5+000 to 8+000 which is likely to advance towards the embankments during next flood season as secondary creek was developed in the above mentioned RD that started to flow towards the embankment and was running parallel along the bank in-front of village bahar wal. Timely intervention is crucial to prevent this secondary creek from evolving into a serious issue, as it can become a potential threat and will not only compromise the strength of the bank but also jeopardize the safety of surrounding inhabitants. .

- HAJIPUR GUJRAN FLOOD BUND OF RIVER RAVI

An Medium Level Flood entered in river Ravi opposite RD 24+000 of Hajipur Gujran flood bund near Kot Nainan and attained the gauge RL 834.00 on 09.07.2023 at 11.00 PM, endured constant for hours and subsided gradually to normal stage on 10.07.2023.

No damage to any structure was observed, all the structures behaved excellently and flood safely passed from Hajipur Gujran flood protection bund beside a parallel flow was observed in between RD 8+000 to 20+000 of Hajipur Gujran flood protection bund opposite to village Dhariwal which needs serious attention. River Ravi enters into Pakistan near to Ayub Ranger post, opposite at RD 8+000 to 9+000 and after flowing in a sharp loop, it turns back to India after damaging vast agriculture land in the area. This sharp bend of River creates spill and a parallel flow along Hajipur Gujran Flood Bund at RD 8+000 to 20+000 upstream of mole head spur No.1. The loop is establishing at very fast pace towards Hajipur Gujran Flood Bund and currently the apex of end of loop is only 2500 ft away from the main bund and very rapidly enhancing towards the main bund and the same distance was 4000 ft in April 2023.

An old Ujh creek exist runs parallel to Hajipur Gujran Flood Bund near its toe. The flow of river entering the territory of Pakistan at Ayub Post remained within the two channels upto the river stage of about 20,000 cusecs. The river flow out-flanks into old Ujh creek at river stage of 30,000 cusecs which runs parallel to the bund. This old Ujh creek is at distance of about 1000 ft away from the sharp loop of River Ravi between RD 9+000 to 13+000 of Hajipur Gujran flood bund.

- BHECO CHAK FLOOD BUND OF RIVER RAVI

Numerous freshets were received in river Ravi during the month of July & August 2022 which heavily engaged the spur No.3 of Bheco Chak Flood Bund and the apron of spur was damaged in length of 240 ft resultantly the pitching was also damaged.  The damage portion was repaired before the onset of flood season 2023 resultantly the sharp loop developed by river Ravi upstream Spur No.3 was completely silted up during the flood season. After being deflected from the head of spur No.3 the river Ravi engaged the nose portion of spur No.4 of Bheco Chak Flood bund during the currents flood season which has resulted in launching of apron of spur No.4.

Since last few years the damaging intrusion of river Ravi in the said reach, is continuously being drifted towards the Right bank due to Indian imposition and the main current of flow is severely damaging the tail portion of Bheco Chak flood bund which is d/s from spur No.5 to tail end of Bheco Chak bund. Consequently, the damaging main current of River is moving smoothly close to the toe of main bund in reach RD 25+500 to 28+500, and have created vulnerability on safety of main bund. The damaging current have encroached towards the toe of main bund and the distance of this river creek from the bund is only 80 ft and likely will assault the main bund during flood season 2024.

- EROSIVE ACTION OF RIVER RAVI D/S BHECO CHAK FLOOD BUND 	AND U/S BALATHOUR CHECK POST

Severe erosive action of river Ravi D/s tail portion of Bheco Chak flood bund and U/s of Balathour Check Post has been observed during this year flood season which has resulted in complete vanishing of village Balaki chak. This erosion has entered a persistent cycle, posing a notable threat to the historical river creek that had long been abandoned. If left unchecked, this phenomenon could result in the detachment of a substantial land area, including numerous villages, critical defense infrastructure, and an expanse of territory. Furthermore, this shift in the flow pattern could exert profound alterations upon the approach towards the corridor encompassing Darbar Sahib Kartarpur. The river in that particular reach has completely eroded a vast land of village Balaki chak and river creek is developing very fast at Bein Nullah near village Madho Gole.

- CHANDIAN DOWEL BUND OF RIVER RAVI

Chandian dowel bund was under direct hit for the last two years. Expert Committee suggested for construction of sloping spur at RD 3+800 & Guide Head Spur at RD 4+600 of Chandian Dowel Bund for protection of Chandian Dowel Bund. Both of spurs were completed before the onset flood season. The spurs behaved excellently and diverted the river away from Chandian Flood Bund which is now flowing about 1000 ft away from the bund. Only small launching of stone at nose portion of spur at RD 3+800 of Chandian Dowel Bund was observed during the freshet received in river Ravi on 10.07.2023.

Although the constructed structures during the last financial year protected the affected reach of Chandian dowel bund between RD 3+000 to 5+000 but the river has started propogating towards RD 0+000 of Chandian main bund which is located at the distance of 1.5 Km downstream of the affected site last year. In the tail portion River Ravi is flowing at the distance of just 33 ft from the toe of the tail mole and continuously approaching towards the bund after taking a sharp loop.

- DEG NULLAH

Deg Nullah received a very high flood of 31,556 Cs on 19.07.2023, High floods of 17563 Cs on 27.07.2023, 15506 Cs on 13.08.2023, 14525 Cs on 14.08.2023, 12553 Cs on 12.09.2023, 17467 Cs on 13.09.2023 and 10193 Cs on 15.09.2023. An inverted Hockey spur is being constructed on recommendation of Departmental Expert at RD 16 - 17/R of Deg Nullah. The partially constructed inverted hockey spur behaved excellently and diverted the main creek in the center of stream during freshets on 19.07.2023, 27.07.2023, 13.08.2023 and 14.08.2023 but while receiving the freshet at velocity of 15 - 18 ft/ Sec, the nose of inverted hockey launched by 10ft in length. The inverted hockey spur pushed the main creek towards left side where after a sharp loop it hit the recently completed solid portion of a spur at RD 18+925/L of Deg Nullah. Although the spur protected embankment on its upstream and downstream but the spur at RD 18+925/L of Deg Nullah itself received severe hit and concentrated flow with high velocity resulted in launching of nose and side slope behind the nose on upstream side in 20 ft length. A pit 15 feet in depth on upstream side of nose was also observed during the frehet on 19.07.2023, 27.07.2023, 13.08.2023 and 14.08.2023. Since the structure is newly constructed and projected 50 ft inside main creek it faced a direct hit of flood water as well as launching of stone. During the freshet of 12553 Cs on 12.09.2023, the main creek moved towards the right side downstream of partially constructed embankment damaging the toe of the embankment but on the left side the main creek shifted away from Spur RD 18+925/L and started hitting the nose of Spur RD 19+500/L and severely damage the spur while washing away its nose during the freshet received on 13.09.2023 and 15.09.2023.

CHAPTER – 4

HISTORIC PEAK FLOOD DATA AND PREVIOUS FIVE YEARS FLOOD DATA OF HEADWORKS / BARRAGES AND OR OTHER CONTROL POINTS

4.1	FLOOD LIMITS

Flood limits of River Ravi and its tributaries as approved by the technical committee are tabulated as under:-

| S No | Sites | Low | Medium | High | Very High | Exceptionally High |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | River Ravi at Jassar | 50000 -75000 | 75000-100000 | 100000-150000 | 150000-200000 | 200000 & above |
| 2 | Ujh Nullah near Jalala | 15000 -30000 (Gauge 851 ft) | 30000 - 50000 (Gauge 853 ft) | 50000 -75000 (Gauge 855 ft) | 75000 & above (Gauge 857 ft) |  |
| 3 | Bein Nullah at Shakargarh Highway Bridge | 1600-3000 | 3000 - 10000 | 10000 -20000 | 20000 -30000 | 30000 & above |
| 4 | Basantar Nullah at Railway Bridge Narowal | 700 - 4700 | 4700 -7500 | 7500 -11600 | 11600 -17800 | 17800 & above |
| 5 | Deg Nullah | 10000 | 10000-15000 | 15000 -22000 | 22000 -30000 | 30000 & above |

Gauges (ft) at Spur No-2 of Hajipur Gujran Flood Bund at Different Flood Stages

| Low Flood | Medium Flood | High Flood | Very High Flood | Exceptionally High Flood |
| --- | --- | --- | --- | --- |
| 830.00 | 834.00 | 836.00 | 838.00 | 839.00 |

4.2 	TIME LAGS OF RIVER RAVI

The time lag depends on many factors such as flood intensity, weather conditions etc. however approximate time lags for the main stations on River Ravi which were experienced in past are given as below.

| Sr.# | REACH | DISTANCE (Mile/Km) | TIME LAG (Hour) |
| --- | --- | --- | --- |
| 01 | Madhupur to Hajipur Gujran Flood Bund | 40 | 6 |
| 02 | Hajipur Gujran Flood Bund to Bheco Chak Flood Bund | 10 | 2 -3 |
| 03 | Bheco chak Flood Bund to Jassar Bridge | 12 | 4 |
| 04 | Jassar Bridge to Ravi Syphon | 38 | 10 |
| 05 | Ravi Syphon to Shahdara Bridge | 33 | 11 |
| 06 | Shahdara Bridge to Balloki Head Works | 64 | 19 |
| 07 | Balloki Head works to Sidhnai Head Works | 240 | 75 |

As per decision of Technical Committee dated 22/07/2000

4.3	HIGHEST FLOODS

Highest Flood 6,50,000 Cs has been recorded in River Ravi in the year 1988.

4.4	FLOOD GAUGING SITES

Flood gauges are installed at different point detail are as under:-

1.       Deg Nullah at Kingra Bridge

2.       Bein Nullah at Shakargarh to Ikhlas road bridge

3.       River Ravi at Spur No.3 of Hajipur Gujran Flood Bund RD.23+450

4.       River Ravi at Jassar.

5. 	 Ujh Nullah at RD.12+200.

6.        Basanter Nullah on Narowal to Shakargarh bridge.

4.5	PEAK DISCHARGE

4.5.1	PEAK DISCHARGE (RIVER RAVI AT JASSAR)

| Sr.# | Date | Gauge | Discharge in Cusecs. |
| --- | --- | --- | --- |
| 1 | 31/7/1989 | 787.20 | 104818 |
| 2 | 09/10/1990 | 783.40 | 58709 |
| 3 | 03/06/1991 | 783.30 | 57758 |
| 4 | 09/11/1992 | 789.60 | 148543 |
| 5 | 07/11/1993 | 789.60 | 136140 |
| 6 | 21/07/1994 | 791.70 | 173090 |
| 7 | 09/05/1995 | 790.70 | 220800 |
| 8 | 24/08/1996 | 788.80 | 151080 |
| 9 | 28/08/1997 | 789.00 | 157600 |
| 10 | 24/09/1998 | 783.80 | 35820 |
| 11 | 20/08/1999 | 782.70 | 23620 |
| 12 | 28/07/2000 | 783.70 | 34480 |
| 13 | 15/08/2001 | 784.50 | 48100 |
| 14 | 14/08/2002 | 785.80 | 69480 |
| 15 | 08/04/2003 | 784.60 | 45135 |
| 16 | 2004 | 782.90 | 31900 |
| 17 | 09/09/2005 | 783.00 | 32669 |
| 18 | 09/04/2006 | 783.50 | 36435 |
| 19 | 21/08/2007 | 781.50 | 22880 |
| 20 | 17/08/2008 | 783.50 | 36435 |
| 21 | 17/08/2009 | 781.00 | 9600 |
| 22 | 21/08/2010 | 785.00 | 21000 |
| 23 | 17/09/2011 | 783.50 | 34360 |
| 24 | 26/08/2012 | 783.30 | 30490 |
| 25 | 08/03/2013 | 787.00 | 67700 |
| 26 | 09/07/2014 | 787.60 | 74600 |
| 27 | 24/09/2015 | 783.80 | 62652 |
| 28 | 27/07/2016 | 783.50 | 36435 |
| 29 | 08/10/2017 | 783.90 | 47494 |
| 30 | 25/09/2018 | 786.20 | 66641 |
| 31 | 18/08/2019 | 785.00 | 51000 |
| 32 | 26/08/2020 | 783.00 | 33000 |
| 33 | 27/07/2021 | 781.50 | 20200 |
| 34 | 16/08/2022 | 786.00 | 63720 |
| 35 | 20/07/2023 | 786.00 | 71010 |

4.5.2  PEAK DISCHARGE (DEG NULLAH AT KINGRA BRIDGE)

| 1 | 23/09/2018 | 896.80 | 19170 |
| --- | --- | --- | --- |
| 2 | 16/08/2019 | 785.10 | 2253 |
| 3 | 26/08/2020 | 894.00 | 3090 |
| 4 | 12/07/2021 | 895.00 | 29783 |
| 5 | 15/08/2022 | 895.00 | 40750 |
| 6 | 19/0/2023 | 894.20 | 31556 |

4.5.3  PEAK DISCHARGE (NULLAH BEIN)

| 1 | 13/08/2018 | 882.00 | 7007 |
| --- | --- | --- | --- |
| 2 | 14/08/2019 | 880.10 | 3946 |
| 3 | 26/08/2020 | 880.50 | 4580 |
| 4 | 27/07/2021 | 880.20 | 4104 |
| 5 | 31/08/2022 | 881.20 | 5722 |
| 6 | 10/08/2023 | 881.00 | 5373 |

4.5.4  PEAK DISCHARGE (NULLAH UJH)

| 1 | 07/08/2018 | 859.00 | 15000 |
| --- | --- | --- | --- |
| 2 | 17/08/2019 | 863.50 | 55000 |
| 3 | 26/08/2020 | 864.00 | 60000 |
| 4 | 20/07/2021 | 864.00 | 60000 |
| 5 | 15/08/2022 | 865.00 | 65000 |
| 6 | 09/07/2023 | 865.00 | 65000 |

4.5.5  PEAK DISCHARGE ( BASANTER NULLAH)

| 1 | 24/09/2018 | 788.30 | 5479 |
| --- | --- | --- | --- |
| 2 | 16/08/2019 | 785.10 | 2253 |
| 3 | 30/08/2020 | 787.20 | 4057 |
| 4 | 10.09.2021 | 786.00 | 2908 |
| 5 | 26/07/2022 | 787.90 | 50114 |
| 6 | 12/08/2023 | 786.00 | 2908 |

CHAPTER – 5

FLOOD FIGHTING STRATEGY

RIVER RAVI

All precautionary measures are adopted before flood season to face any alarming situation at Jassar Bridge on River Ravi, even then arrangements are necessary to avoid heavy damages and flood fighting strategy is adopted in such a way that floods may safely be passed.

In low flood, river water remains within the deep river creek & does not cause any problem on flood bunds & spurs. Watching establishment employed for this purpose remains busy in removing jungle, filling rain cuts & porcupine holes if any.

When water increases beyond 75000 Cs, it will start spreading on adjoining area & also touches the toe of bunds. After the flood water touches the toe of bunds.It becomes necessary to be vigilant & watching of bunds will be started to check any leakage from bunds. Sub Engineers will shift their camps to sites as per duty roaster. Hourly gauges & discharges will be conveyed civil administration & flood warning centers to inform public accordingly.

When river water enters into high flood range, Sub Divisional Officer, Kot Nainan will shift his camp at Spur No. 2 of Hajipur Gujran Flood Protection Bund to supervise staff working on flood protection bunds & spurs and watch the all sites 24 hours.

Two excavators will be kept ready at Hajipur Gujran, Jalala, Bheco Chak comps& Narowal for making cuts closing breaches as & when required according to the circumstances.

NULLAH UJH, JALALA FLOOD BUND

Ujh Nullah experiences flood each year since last five years, hence

- Permanent camp (RD 15 of Jalala Bund) as well as watching with W/C establishment shall be maintained during flood season. Sub Engineer will shift his camp to site during flood season. Hourly gauges & discharges will be conveyed to civil administration & flood warning centers to inform public accordingly

- 01 Excavator along with 03 tractor trolley shall be stationed there during flood to meet any untoward situation.

NULLAH DEG

Similarly, Deg Nullah experiences high flood each year for the last five years, hence

- 02 Permanent camps (each on R/S and L/S of Village Jastiwala) as well as watching with W/C establishment shall be maintained during flood season. Sub Engineers will shift their camps at sites. Hourly gauges & discharges will be conveyed to civil administration & flood warning centers to inform public accordingly

- 02 Excavators along with 04 tractor trollies (L/s and R/s each) at Village Jastiwala camp sites shall be stationed there during flood to meet any unforeseen.

Gauges of different sites especially at Kot Naina spelling and Jassar Bridge for River Ravi, RD 13 of Jalala Bund for Ujh Nullah, Kingra Bridge for Deg Nullah and Narowal to Shakargarh road for  Basanter Nullah  will be noted regularly & recorded. Executive Engineer will inform all agencies especially civil administration as well as army authorities about flood situation. In case of very high flood or exceptionally high flood, meeting will be held in field office with Army & Civil Administration to face the situation.

CHAPTER – 6

FLOOD DAMAGES RESTORATION WORKS

Flood magnitude of 71010 Cusecs (Low Flood) passed during Flood 2023 on 20.07.2023 in river Ravi. An exceptionally high flood of 65000 cusecs and  31556 cusecs was received in Ujh Nullah and Deg Nullah on 09.07.2023 and 19.07.2023 respectively. Frequent events of high flood in Deg Nullah were observed during the flood season 2023. Due to the high flood of 31556 Cusecs in Deg Nullah Spur at RD.18+925/L launching nose and side slopes behind the nose on upstream side in 20 feet length was damaged and nose of spur RD.19+500/L was also damaged during flood season 2023.

The detail of flood restoration works are as under: -

| Sr. No. | Name of restoration work | Status / remarks |  |
| --- | --- | --- | --- |
| 1 | Protecting Hajipur Gujran Flood Bund against erosion of River Ravi between spur No.4 &5. | Work substantially completed. |  |
| 2 | Restoration of damaged Flood Embankment between RD.16+000 to RD.17+000 right side of Deg Nullah. | Damaged during flood season 2022 the restoration work 60% completed during Fiscal year 2022-23. The remaining work revalidated and will be completed during this F/Y. |  |
| 3 | Protection of Daud Rangers Post along right side of River Ravi falling In jurisdiction of Flood Bund Division, Narowal. | Protection work 05% completed during Fiscal year 2022-23. The remaining work revalidated and will be completed during this F/Y. |  |
| 4 | Checking erosive action of the River Ravi at Ishaq forward post. | The erosive action of the River Ravi at Ishaq forward post during floods season 2022 & 2023. Estimate submitted to NESPAK for vetting as per DEC decision 15.01.2024. |  |
| 5 | Protection of Bheco Chak Food Bund against erosion of River Ravi downstream Spur No.5. | Erosive action observed during flood season 2022 & 2023, estimate submitted to NESPAK for vetting as per DEC decision 19.02.2024. |  |
| 6 | Restoration of damaged apron of spur No.4 Bheco Chak Flood Bund. | Damaged apron during flood season 2023. Estimate for restoration of apron has been submitted to NESPAK for vetting |  |
| 7 | Protecting village abadies of Chak Nahra from erosive action of Bein Nullah. | Estimate for Protection of village abadies of Chak Nahra from erosive action of Bein Nullah has been framed submitted to NESPAK for vetting as per decision of DEC. |  |
| 8 | Construction Spur at RD.16+975/R of Deg Nullah. | The estimate for restoration has been submitted to higher office for T.S. |  |
| 9 | Restoration of apron J-Head Spur No.1 Daud Khas Flood Protection Bund. | Damaged during Flood season 2023 and also reported in HSSEU Flood inspection report 2023 | The estimate for restoration is under preparation as per DEC decision. |
| 10 | Checking erosive action between RD.4+000 to RD.5+900 of Chandian Mole Head Spur. |  | The case presented before DEC. The DEC decided 2 No. studs, one at 5+600 and the location of the 2nd will be decided by field formation, PRO (H) and NESPAK after site visit. The estimate will be prepare after finalization of location as per DEC decision. |
| 11 | Restoration Spur at RD.19+500/L of Deg Nullah. |  | The estimate for restoration is under preparation as per DEC decision. |
| 12 | Restoration Spur at RD.18+925/L of Deg Nullah. |  | The estimate for restoration has been submitted to higher office for T.S. |
| 13 | Restoration of solid stone stud at RD.3+800 of Chandian Dowel Bund. |  | The estimate for restoration has been submitted to higher office for T.S. |

NOTE:

M&R works for flood protection bunds are being carried out and will be completed during the year 2023-24.

CHAPTER – 7

FLOOD FIGHTING WATCHING ARRANGEMENTS

7.1	PRE-FLOOD ARRANGEMENTS

The watching establishment on flood protection bunds is required to be employed as per scale & as per Govt. policy. Necessary material will be placed at different sites in order to meet with extra ordinary, worst situation with the site situation. Hence the flood fighting material will be kept ready on head quarter for this purpose.

FLOOD WARNING SYSTEM

The flood warnings received from Gauge at Haji Pur Gujran Bund through wireless installed or otherwise on telephone etc.  The flood condition of the dams and Headworks on Ravi River in India is also received through Flood Warning Center Lahore. On receipt of abnormal flood warning about the stages of flow below Haji Pur Bund, the Deputy Commissioner Narowal and Army Engineer Battalion will be informed by the Executive Engineer / SDO to cope with the flood situation. Close liaison will be kept by the committee members during the flood emergency. The Chief Engineer Irrigation Lahore Zone will also be kept informed about the flood situation constantly.

The flood warning gauges will be received from the following centers:

- Flood warning center Lahore

- Police wireless at Kot Naina

- Flood Camp at HPG Bund

Police wireless control is responsible to collect these gauges 3 hourly in case of high flood and above and 6 hourly in case of low flood to medium flood. These gauges will be conveyed to flood warning center and will be supplied promptly to other concerned authorities.

During rainy / monsoon season, the establishment of Flood Bund Division Narowal will remain very vigilant throughout the monsoon season. Staff of the Division will be set on alert during day and night from 15th June to 15th October. The flood / watching camps will be established at vulnerable points.

7.2	WATCHING ESTABLISHMENT

The normal strength of patrolling for the Flood Protection Bunds and allied spurs consists of 8 Beldars and 1 Mate per mile from 16th April to 15th June, which will be enhanced during the flood season to 16 Beldars and 2 Mates from 16th June to 15th October in shifts.

The normal patrolling with the help of this additional labour will be able to fill up rain cuts gharas and holes of burrowing animals for ensuring the safety against floods.

In addition to above patrol, 3Gauge readers for the observations are regularly posted. During the flood season extra Chowkidars will be employed on the flood watching camps, during flood season for watch and ward arrangements.

7.3	ARRANGEMENT OF SENSITIVE SITES

i.	The normal strength for watching at sensitive sites along flood protection and River training works will be doubled during high flood / exceptionally high flood.

ii.	The establishment can be increased after consultation with Executive Engineer, Flood Bund Division Narowal accordance with site requirements.

The same establishment will be responsible for maintenance of flood bunds and Spurs. It will arrange Minor repairs to bank top, side slopes, removal of Sarkanda etc. as shanks and on pitched part of spurs. Establishment will also be responsible for filling ghares /porcupine holes / rain cuts etc. as occurred due to rains during the monsoon season.

A. POSITION OF RESERVE STOCK ON RIVER TRAINING COMPONENTS

Quantity in Lac Cft

| Sr,No. | Location | Reserve Stone Required as per approved Limit Qty in Lac) | 70 % of approved Limit (Qty in Lac) | Available at site (Qty in Lac) | Balance required w.r.t total approved | Balance required w.r.t 70% of approved Limit (Qty in Lac) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Bheco Chak Flood Protection Bund. | 3.40 | 2.38 | 0.00 | 3.40 | 2.38 | The balance Procurement of Reserve Stock of Stone will be completed before Flood Season 2024. |
| 2 | Hajipur Gujran Flood Protection Bund. | 6.95 | 4.87 | 1.11 | 5.84 | 3.76 |  |
| 3 | Rayya Flood Protection Bund. | 2.00 | 1.40 | 1.61 | 0.39 | 0.00 |  |
| 4 | Chandian Mole Head Spur. | 1.50 | 1.05 | 1.06 | 0.44 | 0.00 |  |
| 5 | Jassar J - Head Spur. | 0.50 | 0.35 | 0.26 | 0.24 | 0.09 |  |
| 6 | Mehdi Dogar T - Cum Hockey Spur. | 0.30 | 0.21 | 0.27 | 0.03 | 0.00 |  |
| 7 | Guide Spur at Chak Narrah. | 0.60 | 0.42 | 0.00 | 0.60 | 0.42 |  |
| 8 | Guide Spur at Village Ferozpur. | 0.80 | 0.56 | 0.00 | 0.80 | 0.56 |  |
| 9 | Jalalam Flood Protection Bund. | 0 | 0 | 0.83 | 0 | 0 |  |
|  | Total:- | 16.05 | 11.24 | 5.14 | 11.74 | 7.21 |  |

7.4	WATCHING MATERIAL

| Sr. | Item | At Narowal | At Shakargarh | Total Required Qty | Available Qty | Balance to be arranged |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Shouldaris Camp tents (Water Proof Good Quality) | 6 | 4 | 10 |  | -- |
| 2. | Camp Tables (Good Quality) | 9 | 9 | 18 |  | -- |
| 3. | Camp Chairs | 48 | 48 | 96 |  | -- |
| 4. | Toot Baskets | 200 | 500 | 700 |  | -- |
| 5. | Empty Gunny Bags (used) | 2500 | 3000 | 5500 |  |  |
| 6. | Swiss cottage Tent | 3 | 4 | 7 |  |  |
| 7. | Sutli | 15 | 45 | 60 kg |  |  |
| 8. | Needles. | 12 | 20 | 32 No |  |  |
| 9. | Killas | 100 | 200 | 300 No |  |  |
| 10. | Flood Lights | 6 | 12 | 18 No |  |  |
| 11. | Wooden Hammers | 6 | 4 | 10 No |  |  |
| 12. | Kassies | 100 | 200 | 300 No |  |  |
| 13. | Axes | 10 | 15 | 25 No |  |  |
| 14. | Manila Rope | 200 | 400 | 600 kg |  |  |
| 15. | Life Jacket | 10 | 24 | 34 No |  |  |
| 16. | Generator (Capacity 3-KVA) | 2 | 4 | 6 No |  |  |
| 17. | Electric Cable 7/0029 | 6 | 8 | 14 Coil |  |  |
| 18. | Electric Cable 3/0029 | 6 | 8 | 14 Coil |  |  |
| 19. | Electric Switch | 45 | 45 | 90 No |  | -- |
| 20. | Holders | 100 | 260 | 360 No |  | -- |
| 21. | Portable Lights | 50 | 50 | 100 No | -- |  |
| 22. | Energy Saver 45 W | 70 | 70 | 140 No |  |  |
| Sr. | Item | At Narowal | At Shakargarh | Total Required Qty | Available Qty | Balance to be arranged |
| 23. | Energy Saver 25 W | 70 | 70 | 140 No |  |  |
| 24. | Bamboos 8’-10’ long (For Lighting arrangements) | 150 | 150 | 300 No |  |  |
| 25. | Petrol for Running Generator | 2000 | 2500 | 4500 Ltr |  |  |
| 26. | Steel Charpoy | 12 | 12 | 24 No |  |  |
| 27. | Folding Table | 6 | 4 | 10 No |  |  |
| 28. | Folding Chair | 12 | 12 | 24 No |  |  |
| 29. | Polyproplyne bags 50 kg capacity | 5000 | 6000 | 11000 No |  |  |
| 30. | Hand Saw | 6 | 9 | 15 No |  |  |
| 31. | Wire Rope 1/2" | 200 | 600 | 800 Rft |  |  |
| 32. | Naylon Rope 3/8" | 100 | 200 | 300 Kg |  |  |
| 33. | Naylon Rope3/4" | 100 | 300 | 400 Kg |  |  |
| 34. | Naylon Rope 1/4" | 100 | 200 | 300 Kg |  |  |
| 35. | Umbrellas | 12 | 18 | 30 No |  |  |
| 36. | Rain Coats | 12 | 18 | 30 No |  |  |
| 37. | Water Cooler | 6 | 4 | 10 No |  |  |
| 38. | Water set | 6 | 4 | 10 No |  |  |
| 39. | First Aid Box | 6 | 4 | 10 No |  |  |
| 40. | Lifebuoy | 12 | 12 | 24 No |  |  |

Note:-	Balance quantity of flood fighting material will be procured before the start of flood season 2024 and material is stored at available/ safe custody at Sub Divisional arrangements.

7.5	ARRANGEMENT OF SOUNDING AND PROBING

In case of any situation on flood protection and River training works, sounding and probing arrangement will be made for which proper equipment are already available in this Division.

7.6	LIGHTING ARRANGEMENT

To avoid all the chances of electricity, break down, additional lighting arrangements parallel to existing system i.e WAPDA supply will be arranged. For generation power to be very reliable generating set, with 2 No stand by units are available in emergent situation.

7.7	RATION ARRANGEMENT

The area in the jurisdiction of this division falls in the District, i – Narowal, ii- Sialkot, iii- Sheikhupura. In case of high flood in River Ravi / tributaries, a separate plan will be prepared, the concerned PDMA authorities, District Administration and relevant Food department will mobilize their sources for supplying food for Human and cattle population.

7.8	POL ARRANGEMENT FOR VEHICLE

P.O.L facilities / arrangement will be made by the Irrigation Department through Civil Administration.

7.9	TRANSPORTATION

Transportation facilities will be provided by the Civil Authorities

7.10	LAW AND ORDER

Law and order situation will be tackled by the Civil Administration with the help of Police Department.

7.11	MEDICAL ARRANGEMENT FOR LABOUR

Health Department will be responsible for mobilizing their sources for carrying out necessary operation for providing medical facilities to the labour.

7.12	LIAISON WITH OTHER DEPARTMENT

The Executive Engineer, Flood Bund Division, Narowal will perform following functions with in his administrative jurisdiction for the better and effective flood management.

- Periodic review of structural integrity of flood infrastructure over river Ravi in order to ensure that no breach may occurs in the event of heavy discharge of water. The Executive Engineer will share his observation with his supervisory officer as well as District Administration, well before on set of Flood season in order to take necessary action accordingly.

- Identification of vulnerable points on river training works and flood protection works where breach may occur and specification of locations for positioning of requisite machinery / material near the vulnerable points.

- Maintenance and repair to flood protection and river training works infrastructures.

- Joint inspection of Flood protection infrastructure with District Administration.

- Collection and sharing of information regarding discharge in Ravi, with the Military Authorities as well as District Administration on daily basis.

- Collection of information on discharge, from monitoring check points on River Ravi as well as control center at Shakargarh.

- Improvement of existing instruction / gauges used for determination of water discharge (Cusecs) in Ravi.

- Development of more effective early warning system.

- Liaison with flood forecasting center Lahore for collection of flood related information.

- Briefing of authorities concerned on Flood protection arrangements and development of an integrated departmental strategy, to be able to combat any situation during Floods.

- Stock piling of essential articles to combat any flood related contingency and arrangements of sufficient funds beforehand, for such purposes.

- Arrangements of labour along with machinery / equipment for proper maintenance of the vulnerable pints on flood protections arrangements.

- Identification of points on road or otherwise, where breaches / cuts are required to be made to further facilitate discharge of water in order to avert larger catastrophe.

- Ascertainment of extent of damages caused to the protection bunds and other installation after flood water subsides.

- Initiation of criminal proceeding against elements involved in will full breach in flood protection arrangements on any canal, with consent of competent authority.

- Assistance and coordination with other departments for providing early relief to the public in emergency situation.

7.13	ROLE OF ARMY

During flood emergency, Deputy Commissioner, in consultation with Executive Engineer, Flood Bund Division Narowal will inform 30-Corp Engineers Gujranwala about flood situation. Upon intimation, concerned army authorities alongwith District Administration will perform activities to manage flood emergency during Flood 2024.

7.14	DUTIES OF TELEPHONE ATTENDANT

The duty of telephone attendant is to apprise the Department / Civil Administration about the flood situation during the rain / flood season i.e. 15.06.2024 to 15.10.2024.

7.15	WIRELESS ARRANGEMENTS

Wireless system / arrangement will be made for the vehicles under use of Officers of Flood Bund Division Narowal, of Link Circle Lahore during the period of 15 June 2024 to 15 October 2024.

CHAPTER – 8

DETAIL OF ENCROACHMENT

There is no encroachment on flood protection works and river training works in the jurisdiction of Flood Bund Division Narowal causing hindrance to the movement of flood fighting machinery on or along the flood protection structures during any flood emergency.

| Type of Encroachment | Total No of Encroachments | Encroachments Removed | Balance To be Removed | Action to be Taken |
| --- | --- | --- | --- | --- |
| Ordinary | NIL |  |  |  |
| Critical | NIL |  |  |  |

Executive Engineer,

Flood Bund Division,

Narowal.

Sub Divisional Officer,

Flood Bund Sub Division No.1,

Shakargarh

Sub Divisional Officer,

Sialkot Drainage Sub Division,

Narowal

CHAPTER – 9

DUTY ROSTER / FLOOD FIGHTING PROGRAMME

Duty establishment required for watching arrangements in 3 shifts round the clock will be under the control of in-charge Sub Engineer of concerned Section. Sub Divisional Officers, Flood Bund Sub Division No.1 Shakargarh and Sialkot Drainage Sub Division Narowal will be overall in-charge and will exercise surprise check in their respective jurisdiction.

A. Flood Bund Sub Division No.1 Shakargarh.

| Flood Situation. | Officer/Officials on duty | Head quarter / Camp | No of Shifts / Time | Temporary/work charge Establishment per shift each section |
| --- | --- | --- | --- | --- |
| Low Flood | Sub Divisional officer Sub Engineer Jalala Bund Sub Engineer Haji Pur Bund Sub Engineer S&I Sec Sub Engineer Bheco chak Bund | -RD 15+000 -Spur No,2 -Tie Bund -RD 26+000 | 3 / 08-16 hrs 16-24 hrs 24-08 hrs | Mate = 1 No. Beldar = 2 No & Supporting staff. |
| Medium Flood | Sub Divisional officer Sub Engineer Jalala Sec Sub Engineer Haji Pur Sec Sub Engineer S&I Sec Sub Engineer Bheco chak Section | RD 15+000 -Spur No,2 -Tie Bund -RD 26+000 | 3 / 08-16 hrs 16-24 hrs 24-08 hrs | Mate = 2 No. Beldar = 3 No & Supporting staff. |
| High Flood | Sub Divisional officer Sub Engineer Jalala Sec Sub Engineer Haji Pur Sec Sub Engineer S&I Sec Sub Engineer Bheco chak Section | RD 15+000 -Spur No,2 -Tie Bund -RD 26+000 | 3 / 08-16 hrs 16-24 hrs 24-08 hrs | Mate = 2 No. Beldar = 10 No & Supporting staff. |
| Very High Flood | Executive Engineer Flood Bund Division Sub Divisional officer Sub Engineer Jalala Sec Sub Engineer Haji Pur Sec Sub Engineer S&I Sec Sub Engineer Bheco chak Section | RD 15+000 -Spur No,2 -Tie Bund -RD 26+000 | 3 / 08-16 hrs 16-24 hrs 24-08 hrs | Mate = 3 No. Beldar = 20 No & Supporting staff. |
| Exceptional High Flood | Executive Engineer Flood Bund Division Sub Divisional officer Sub Engineer Jalala Sec Sub Engineer Haji Pur Sec Sub Engineer S&I Sec Sub Engineer Bheco chak Section | RD 15+000 -Spur No,2 -Tie Bund -RD 26+000 | 3 / 08-16 hrs 16-24 hrs 24-08 hrs | Mate = 4 No. Beldar = 30 No & Supporting staff. |

B. Sialkot Drainage Sub Division Narowal.

| Low Flood | Sub Divisional officer Sub Engineer Jassar Sec Sub Engineer Chandian Sec Sub Engineer Rayya Sec Sub Engineer Zafarwal Sec | - J-Spur -Dowel bund -Pejowali hut -RD 75+000 | 3 / 08-16 hrs 16-24 hrs 24-08 hrs | Mate = 1No. Beldar = 2No & Supporting staff. |
| --- | --- | --- | --- | --- |
| Medium Flood | Sub Divisional officer Sub Engineer Jassar Sec Sub Engineer Chandian Sec Sub Engineer Rayya Sec Sub Engineer Zafarwal Sec | - J-Spur -Dowel bund -Pejowali hut -RD 75+000 | 3 / 08-16 hrs 16-24 hrs 24-08 hrs | Mate = 2No. Beldar = 3No & Supporting staff. |
| High Flood | Executive Engineer Flood Bund Division Sub Divisional officer Sub Engineer Jassar Sec Sub Engineer Chandian Sec Sub Engineer Rayya Sec Sub Engineer Zafarwal Sec | - J-Spur -Dowel bund -Pejowali hut -RD 75+000 | 3 / 08-16 hrs 16-24 hrs 24-08 hrs | Mate = 2No. Beldar = 10No & Supporting staff. |
| Very High Flood | Executive Engineer Flood Bund Division Sub Divisional officer Sub Engineer Jassar Sec Sub Engineer Chandian Sec Sub Engineer Rayya Sec Sub Engineer Zafarwal Sec | - J-Spur -Dowel bund -Pejowali hut -RD 75+000 | 3 / 08-16 hrs 16-24 hrs 24-08 hrs | Mate = 3No. Beldar = 20No & Supporting staff. |
| Exceptional High Flood | Executive Engineer Flood Bund Division Sub Divisional officer Sub Engineer Jassar Sec Sub Engineer Chandian Sec Sub Engineer Rayya Sec Sub Engineer Zafarwal Sec | - J-Spur -Dowel bund -Pejowali hut -RD 75+000 | 3 / 08-16 hrs 16-24 hrs 24-08 hrs | Mate = 4No. Beldar = 30No & Supporting staff. |

2. No. additional camps will be maintained by the Sialkot Drainage Sub Division Narowal at RD 16-L and RD 38/R of Deg Nullah, simultaneously.

Note:-

*	Executive Engineer Flood Bund Division Narowal is the overall In-charge of the whole operation during very high and exceptionally high flood.

*	All the Sub Engineers will perform their duties assigned above along with their establishment equipped with necessary T & P articles.

*	However, the duties of adjoining Sub Engineers with their establishment would be called any time any where and at any point as desired and required by the SDO's In-charge under intimation to Executive Engineer Flood Bund Division Narowal the In-charge of whole operation.

CHAPTER – 10

EMERGENCY TELEPHONE NOs

| Sr.# | Name of Officers | Office | Residence |
| --- | --- | --- | --- |
| 1 | Secretary Irrigation Department Lahore | 042-99212117 042-99212118 | 042-99200954 |
| 2 | Deputy Secretary Operation Irrigation Lahore. | 042-99112127 | 042-9212129 |
| 3 | Chief Monitoring (PMIU) Lahore. | 042-99213595 042-99213597 | Toll Free No. 0800-11333 |
| 4 | Chief Engineer Drainage & Flood Lahore | 042-99230602 |  |
| 5 | Chief Engineer Irrigation Lahore. | 042-99212086 | 0300-4017310 |
| 6 | Superintending Engineer Link Circle, Lahore. | 042-99250310 | 0332-5543633 |
| 7 | Director Flood Lahore | 042-99231614 |  |
| 8 | Deputy Director Flood Lahore | 042-99230282 |  |
| 9 | Flood Warning Center Lahore. | 042-99205157 | 042-99205158 |
| 10 | Flood Control Center Narowal. | 0542-920090 |  |
| 11 | Executive Engineer Flood Bund Division, Narowal | 0542-920090 | 0301-1302162 |
| 12 | Executive Engineer Operation Lahore Zone, (FLOOD EMERGENCY OFFICER) | 042-99212089 |  |
| 13 | Deputy Commissioner, Narowal | 0542-9201210-20 |  |
| 14 | Additional District Collector (Revenue), Narowal | 0542-920013-15 |  |
| 15 | Assistant Commissioner, Narowal. | 0542-920022 |  |
| 16 | Assistant Commissioner, Shakargarh | 0542-450474 |  |
| 17 | Executive Engineer Lahore Drainage Division | 042-99250399 |  |
| 18 | Executive Engineer Rachna Drainage Division Sheikhupura. | 056-9200250 |  |
| 19 | Sub Divisional Officer Flood Bund Sub Division No.1 Shakargarh. |  | 0321-7436970 |
| 20 | Sub Divisional Officer Sialkot Drainage Sub Division. Narowal. | 0542-920091 | 0300-4975037 |
| 21 | Head Signaler Telegraph Office Lahore. | 0304-7056225 | 0302-4990827 |
| 22 | Commanding Officer, 23 Engineers, Battalion, Sialkot | 052-5715184 |  |
| 23 | Commanding Officer, HQ Engineers, 23 Corps, Gujranwala. | 055-2692353 |  |
| 24 | District Police Officer, Narowal | 0542-412800 | 0542-412200 |

DISTRICTS ADMINISTRATION

| Sr.# | Address | Office | Residence |
| --- | --- | --- | --- |
| 1 | Commissioner Gujranwala Division | 0542-9201210-20 |  |
| 2 | Deputy Commissioner Narowal | 0542-9201210-20 |  |
| 3 | Deputy Commissioner Sialkot | 052-9250451-52 |  |
| 4 | Assistant Commissioner Narowal | 0542-920022 |  |
| 5 | Assistant Commissioner Shakargarh | 0542-450474 |  |
| 6 | Assistant Commissioner Pasrur | 052-9250451-52 |  |
| 7 | District Police Officer Narowal. | 0542-412800 |  |
| 8 | District Police Officer Sialkot. | 052-9250321-2 |  |
| 9 | Sub Divisional Police Officer Narowal | 0542-920091 |  |
| 10 | Sub Divisional Police Officer Shakargarh | 0542-450800 |  |
| 11 | SDPO Pasrur | 052-6442626 |  |
| 12 | Police Station Sadar Pasrur | 052-6442323 |  |
| 13 | Police Station Kot Nainan | 0542-625946 |  |
| 14 | NTO / Dealing Official D.C Office Narowal / Javed Naseem | 0300-7760280 |  |
| 15 | Rescue 1122 Narowal | 1122 |  |

CHAPTER – 11

STANDARD OPERATING PROCEDURE (SOP)

FOR BREACHING SECTION

11.1 HISTORY OF THE BREACHING SECTION

11.2	LOCATION, DESIGN, QUANTITY AND VARIETY OF THE 	EXPLOSIVE REQUIRED FOR DETONATION .

There is no breaching Section under control of Flood Bund Division Narowal

DESIGN OF BREACHING SECTION

Not Applicable

QUANTITY AND VARIETY OF THE EXPLOSIVE REQUIRED FOR DETONATION

Not Applicable

11.3	ARRANGEMENTS OF EXPLOSIVE AND SECURITY OF EXPLOSIVE STORES

Not Applicable

11.4	LIST OF THE SECURITY STAFF ALONG WITH DETAIL OF THEIR TRAINING etc.

Not Applicable

11.5	DETAIL OF MECHANICAL MEANS AS STANDBY	ARRANGEMENTS IN CASE OF DETONATION FAILURE

Not Applicable

  - DUTY ROSTER IN CASE OF CRITICAL SITUATION

Not Applicable

11.7	BREACHING COMMITTEE WITH THEIR ACTION PLAN

Not Applicable

11.8LIST OF THE VILLAGE LIKELY TO BE INUNDATED IN 	CASE OF BREACH

Not Applicable

11.9	ANNOUNCEMENT AND DETAIL OF EVACUATION 	ARRANGEMENTS

Not Applicable

11.10DETAILS OF COORDINATION WITH CIVIL / PAK ARMY AUTHORITIES

Not Available

11.11 PARALLEL COMMUNICATION ARRANGEMENTS

The communication arrangements will be supplemented through police wireless network installation at Police station Kot Nainan linked up with flood warning center, Lahore. The communication will help to receive the latest flood situation of all the respective sites. The information will be communicated to the District formation and Army authorities.

11.12 INDEX PLAN

PART - B

CHAPTER - 12

VULNERABLE SITES ON FLOOD BUNDS/STRUCTURE

12.1	APPREHENDED BREACHES IN FLOOD BUNDS / STRUCTURES.

}

Details of Vulnerable Sites are as under:-

- Chandian Dowl Bund From RD.3+000 to 5+000

- Jalala Flood Bund between RD.13+000 to 18+000

Vulnerable site

Bheco Chak Flood Bund from RD.25+000 to

RD.29+0000.

- Hajipur Gujran between Spur 4 & 5.

- Deg Nullah RD16+000 to 17+000/R

- Deg Nullah RD.18+000 to 20+000/L

12.2	OPERATION OF BREACHING SECTION.

Not Applicable

12.3	BREACHES DUE TO RISE OF FLOOD WATER, DETERIORATION OF FLOOD BUNDS.

There is no breach was occurred due to rise of flood water during flood season 2023.

CHAPTER - 13

EMERGENCY CONTINGENCY / PLAN FOR VULNERABLE SITES

PLAN

A

- EMERGENCY CONTINGENCY PLAN FOR VULNERABLE REACH CHANDIAN DOWEL BUND FROM RD 3+000 TO 5+000

CHANDIAN DOWEL BUND

CAMP SITE at RD 2+000

13.1  PLAN SHOWING ROUTE OF FLOOD WATER COMING OUT THE BREACH.

1. CHANDIAN DOWEL BUND FROM RD 3+000 TO 5+000

13.2	DETAIL OF VILLAGE ABADIES LIKELY TO BEAFFECTED AND THISALSO BE SHOWN ON THE PLAN

Baseke, Ranwan, Chandianwali,  Chak Bathindah,  Chailianwali, Doolam, Khral, Mahar Sharif,     Kotli Hasan Shah, Nangle, Nadir, Sotia Bambia.

13.3	STRATEGY AND ACTION TO BE TAKEN,

13.3.1ARRANGEMENTS.

The necessary repairs of the flood bund, works will be carried out before start of flood season. Moreover, arrangements to establish flood camps will be ensured and deficient quantity of flood fighting material and equipment will be procured before time for watching during flood season.

The flood fighting material will be kept in stores which are located in the premises of flood watching camp under the control/ custody of the Sub Engineers concerned.

13.3.2 ESTABLISHMENT OF FLOOD FIGHTING CAMPS

The Flood Fighting camps will be arranged at RD.2+00 of Dowel Bund as per requirements according to flood situation.

13.3.3DUTIES OF OFFICER / OFFICIALS AND THEIR CAMP SITES

| Sr, No | Flood Situation. | Officer/Officials on duty (Name, Designation, Cell No.) | Camp Location |
| --- | --- | --- | --- |
| 1 | Low Flood | M. Moazzam Ali, Sub Divisional officer, 0300-4975037 M. Arslan, Sub Engineer Chandian, 0301-2979301 M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 Mehmood Ahmad, Sub Engineer Zafarwal, 0300-6978519 | - Dowel Bund -Pejowali Hut -Spur RD 75 |
| 2 | Medium Flood | M. Moazzam Ali, Sub Divisional officer, 0300-4975037 M. Arslan, Sub Engineer Chandian, 0301-2979301 M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 Mehmood Ahmad, Sub Engineer Zafarwal, 0300-6978519 | - Dowel Bund -Pejowali Hut -Spur RD 75 |
| 3 | High Flood | M. Moazzam Ali, Sub Divisional officer, 0300-4975037 M. Arslan, Sub Engineer Chandian, 0301-2979301 M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 Mehmood Ahmad, Sub Engineer Zafarwal, 0300-6978519 | -Dowel Bund -Pejowali Hut -Spur RD 75 |
| 4 | Very High Flood | Ali Raza, Executive Engineer, 0301-1302162 M. Moazzam Ali, Sub Divisional officer, 0300-4975037 M. Arslan, Sub Engineer Chandian, 0301-2979301 M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 Mehmood Ahmad, Sub Engineer Zafarwal, 0300-6978519 | -Dowel Bund -Pejowali Hut -Spur RD 75 |
| 5 | Exceptionally Flood | Ali Raza, Executive Engineer, 0301-1302162 M. Moazzam Ali, Sub Divisional officer, 0300-4975037 M. Arslan, Sub Engineer Chandian, 0301-2979301 M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 Mehmood Ahmad, Sub Engineer Zafarwal, 0300-6978519 | -Dowel Bund -Pejowali Hut -Spur RD 75 |

Note:-

*	Executive Engineer Flood Bund Division Narowal will be the over all In-charge of the whole operation during very high and exceptionally high flood.

*	All the Sub Engineer will perform their duties assigned above along with their establishment with necessary T & P.

*	However the duties of remaining Sub Engineers with their establishment would be called any time any where and at any point as desired and required by the Sub Divisional Officer In-charge under intimation to Executive Engineer Flood Bund Division Narowal the In-charge of whole operation.

13.3.4 DEPARTMENTAL MACHINERY AVAILABLE

One number Tractor with hydraulic Trolley&Boozer is available.

13.3.5MACHINERY AVAILABLE FROM PRIVATE SOURCE.

Machinery will be arranged if required from enlisted Government Contractors.

13.3.6  FLOOD FIGHTING MATERIAL REQUIRED.

13.3.7  FLOOD FIGHTING MATERIAL AVAILABLE.

| Sr. | Name of Article | Total Quantity Required | Available Quantity | Balance Quantity | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1. | Shouldaris/ Camp tents (Water Proof Good Quality) | 1 | 0 | 1 | The balance quantity will be procured before the onset of the Flood Season 2024 |
| 2. | Camp Tables (Good Quality) | 2 | 0 | 2 |  |
| 3. | Camp Chairs | 12 | 0 | 12 |  |
| 4. | Baskets | 46 | 0 | 46 |  |
| 5. | Empty Gunny Bags (used) | 633 | 0 | 633 |  |
| 6. | Swiss Cottage Tent | 1 | 0 | 1 |  |
| 7. | Sutli | 3 | 0 | 3 |  |
| 8. | Needles. | 3 | 0 | 3 |  |
| 9. | Killas | 20 | 0 | 20 |  |
| 10. | Flood Lights | 1 | 0 | 1 |  |
| 11. | Wooden Hamers | 1 | 0 | 1 |  |
| 12. | Kassaies | 20 | 0 | 20 |  |
| 13. | Axes | 2 | 0 | 2 |  |
| 14. | Manila Rope | 50 | 0 | 50 |  |
| 15. | Life Jacket | 2 | 0 | 2 |  |
| 16. | Generator (Capacity 3-KVA) | 1 | 0 | 1 |  |
| 17. | Electric Cable 7/0029 | 2 | 0 | 2 |  |
| 18. | Electric Cable 3/0029 | 2 | 0 | 2 |  |
| 19. | Switch | 15 | 0 | 15 |  |
| 20. | Holders | 25 | 0 | 25 |  |
| 21. | Portable Lights | 15 | 0 | 15 |  |
| 22. | Energy Saver 45 W Philips | 20 | 0 | 20 |  |
| 23. | Energy Saver 25 W Philips | 20 | 0 | 20 |  |
| 24. | Bamboos 8’-10’ long (For Lighting arrangements) | 50 | 0 | 50 |  |
| 25. | Petrol for Running Generator | 400 Ltr | 0 | 400 Ltr |  |
| 26. | Steel Charpoy | 3 | 0 | 3 |  |
| 27. | Folding Table | 1 | 0 | 1 |  |
| 28. | Folding Chair | 2 | 0 | 2 |  |
| 29. | Polyproplyne bags 50 kg capacity | 1000 | 0 | 1000 |  |
| 30. | Hand Saw | 1 | 0 | 1 |  |
| 31. | Wire Rope 1/2" | 50 | 0 | 50 |  |
| 32. | Naylon Rope 3/8" | 20 | 0 | 20 |  |
| 33. | Naylon rope3/4" | 20 | 0 | 20 |  |
| 34. | Naylon Rope 1/4" | 20 | 0 | 20 |  |
| 35. | Umbrellas | 2 | 0 | 2 |  |
| 36. | Rain Coats | 2 | 0 | 2 |  |
| 37. | Water Cooler | 1 | 0 | 1 |  |
| 38. | Water set | 1 | 0 | 1 |  |
| 39. | First Aid Box | 1 | 0 | 1 |  |
| 40. | Lifebuoy | 2 | 0 | 2 |  |

NOTE:-	Balance quantity of flood fighting material will be procured before the start of flood season 2024 and material is stored at camp site.

13.4	DETAIL OF OTHER INFRASTRUCTURE LIKE ELECTRICITY, SUI GAS, TELEPHONEINSTALLATION, ROAD NETWORK, OTHER BUILDING, CANAL AND DRAINAGE NETWORK

CHANDIAN DOWEL BUND RD 3+000 TO 5+000

The following Irrigation and roads networks shall be affected in case of breach.

DETAIL OF IRRIGATION NETWORK ON RIGHT SIDE

| Sr.# | Name of Channel / Bund | From RD. | To RD. |
| --- | --- | --- | --- |
| 1 | Rayya Flood Bund | 7+000 | 65+000 |
| 2 | Mehdi Dogar Bund | 0+000 | 3+300 |
| 3 | Spurs along Daud Flood Bund | 0 | 5300 |
| 4 | Jhajri Drain | 0 | 13000 |

DETAIL OF ROAD NETWORK

| Sr.# | Name of Village | Population | Detail of Infrastructure |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Boys school | Girl school | Health Centers | Tel: Exchange | Misc: | Road |
| 1 | Baseke | 5500 | 1 | 1 | -- | -- | -- | 1 |
| 2 | Daie wala | 980 | 1 | 1 | 1 | -- | -- | 1 |
| 3 | Rawan | 1200 | 1 | 1 | -- | -- | -- | 1 |
| 4 | Chak Bathinda | 300 | -- | -- | -- | -- | -- | 1 |
| 5 | Chandianwali | 1100 | 1 | 1 | -- | -- |  | 1 |
| 6 | Mahar Sharif | 1500 | 1 | 1 | -- | -- | -- | 1 |
| 7 | Chailawali | 1183 | 1 | 1 | 1 | -- | -- | 1 |
| 8 | Dulam | 1551 | 1 | 1 | -- | -- | -- | 1 |
| 9 | Kharl | 738 | 1 | 1 | -- | -- | -- | 1 |
| 10 | Kotli hasan Shah | 2829 | 1 | 1 | -- | -- | -- | 1 |
| 11 | Nangal | 200 | -- | -- | -- | -- | -- | 1 |
| 12 | Nadeer | 335 | -- | -- | -- | -- | -- | 1 |
| 13 | Sutia Bambia | 933 | 1 | 1 | -- | -- | -- | 1 |
| Total |  | 18349 | 10 | 10 | 2 | 0 | 0 | 13 |

CHAPTER - 13

EMERGENCY CONTINGENCY / PLAN FOR VULNERABLE SITES

PLAN

B

- EMERGENCY CONTINGENCY PLAN FOR VULNERABLE REACH JALALA FLOOD BUND BETWEEN RD.13+000 TO 18+000

13.1  PLAN SHOWING ROUTE OF FLOOD WATER COMING OUT THE BREACH.

- JALALA FLOOD BUND BETWEEN RD.13+000 TO 18+000

13.2	DETAIL OF VILLAGE ABADIES LIKELY TO BE AFFECTED 	AND 	THISALSO BE SHOWN ON THE PLAN

Chak Jhandar, Warch, Jalala, Fatah,Ahsanpur, Bakarwal, Chainal, Karouual,

13.3	STRATEGY AND ACTION TAKEN, EXPLAINED IN 	DETAIL. THIS MAYINCLUDE

The necessary repairs of the flood bund works will be carried out before start of flood season. Moreover, arrangements to establish flood camps will be ensured and deficient quantity of flood fighting material and equipment will be procured before time for watching during flood season.

The flood fighting material will be kept in stores which are located in the premises of Stores under the control/ custody of the Sub Engineers concerned.

13.3.1	ARRANGEMENTS.

Flood fighting camp will established at 13+000 of Jalala Flood Bund

13.3.2	ESTABLISHMENT OF FLOOD FIGHTING CAMPS

The Flood Fighting camps will be arranged at 13+000 of Jalala Flood Bund as per requirements according to flood situation.

13.3.3	DUTIES OF OFFICER / OFFICIALS AND THEIR CAMP SITES

| Sr, No | Flood Situation. | Officer/Officials on duty (Name, Designation, Cell No.) | Camp Location |
| --- | --- | --- | --- |
| 1 | Low Flood | Ahsan Naveed, Sub Divisional officer, 0321-7436970 Mr. M. Ijaz Sub Engineer Jalala Bund, 0335-1613955 Abdul Kareem, Sub Engineer Haji Pur Bund 0301-6332951 Abdul Kareem, Sub Engineer S&I Sec 0301-6332951 M. Ijaz, Sub Engineer Bheco chak Bund, 0335-1613955 | -RD 13+000 -RD 20+000 -Tie Bund -RD 26+000 |
| 2 | Medium Flood | Ahsan Naveed, Sub Divisional officer, 0321-7436970 Mr. M. Ijaz Sub Engineer Jalala Bund, 0335-1613955 Abdul Kareem, Sub Engineer Haji Pur Bund 0301-6332951 Abdul Kareem, Sub Engineer S&I Sec 0301-6332951 M. Ijaz, Sub Engineer Bheco chak Bund, 0335-1613955 | -RD 13+000 -RD 20+000 -Tie Bund -RD 26+000 |
| 3 | High Flood | Ahsan Naveed, Sub Divisional officer, 0321-7436970 Mr. M. Ijaz Sub Engineer Jalala Bund, 0335-1613955 Abdul Kareem, Sub Engineer Haji Pur Bund 0301-6332951 Abdul Kareem, Sub Engineer S&I Sec 0301-6332951 M. Ijaz, Sub Engineer Bheco chak Bund, 0335-1613955 | -RD 13+000 -RD 20+000 -Tie Bund -RD 26+000 |
| 4 | Very High Flood | Ali Raza, Executive Engineer, 0301-1302162 Ahsan Naveed, Sub Divisional officer, 0321-7436970 Mr. M. Ijaz Sub Engineer Jalala Bund, 0335-1613955 Abdul Kareem, Sub Engineer Haji Pur Bund 0301-6332951 Abdul Kareem, Sub Engineer S&I Sec 0301-6332951 M. Ijaz, Sub Engineer Bheco chak Bund, 0335-1613955 | RD 38+000 -RD 20+000 -Tie Bund -RD 26+000 |
| 5 | Exceptionally Flood | Ali Raza, Executive Engineer, 0301-1302162 Ahsan Naveed, Sub Divisional officer, 0321-7436970 Mr. M. Ijaz Sub Engineer Jalala Bund, 0335-1613955 Abdul Kareem, Sub Engineer Haji Pur Bund 0301-6332951 Abdul Kareem, Sub Engineer S&I Sec 0301-6332951 M. Ijaz, Sub Engineer Bheco chak Bund, 0335-1613955 | -RD 38+000 -RD 20+000 -Tie Bund -RD 26+000 |

13.3.4 DEPARTMENTAL MACHINERY AVAILABLE

One number Tractor with hydraulic trolley & Boozer is available.

13.3.5 MACHINERY AVAILABLE FROM PRIVATE SOURCE.

Machinery will be arranged if required from enlisted Government Contractors.

13.3.6 FLOOD FIGHTING MATERIAL REQUIRED.

13.3.7 FLOOD FIGHTING MATERIAL AVAILABLE

| Sr. | Name of Article | Total Quantity Required | Available Quantity | Balance Quantity | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1. | Shouldaris/ Camp tents (Water Proof Good Quality) | 1 | 0 | 1 | The balance quantity will be procured before the onset of the Flood Season 2024 |
| 2. | Camp Tables (Good Quality) | 2 | 0 | 2 |  |
| 3. | Camp Chairs | 12 | 0 | 12 |  |
| 4. | Baskets | 100 | 0 | 100 |  |
| 5. | Empty Gunny Bags (used) | 800 | 0 | 800 |  |
| 6. | Chouldaries. | 1 | 0 | 1 |  |
| 7. | Sutli | 12 | 0 | 12 |  |
| 8. | Needles. | 5 | 0 | 5 |  |
| 9. | Killas | 50 | 0 | 50 |  |
| 10. | Flood Lights | 3 | 0 | 3 |  |
| 11. | Wooden Hamers | 1 | 0 | 1 |  |
| 12. | Kassaies | 50 | 0 | 50 |  |
| 13. | Axes | 4 | 0 | 4 |  |
| 14. | Manila Rope | 100 | 0 | 100 |  |
| 15. | Life Jacket | 6 | 0 | 6 |  |
| 16. | Generator (Mitsubushi Diesel PS .35 Capacity 3-KV | 1 | 0 | 1 |  |
| 17. | Electric Cable 7/0029 | 2 | 0 | 2 |  |
| 18. | Electric Cable 3/0029 | 2 | 0 | 2 |  |
| 19. | Switch | 15 | 0 | 15 |  |
| 20. | Holders | 65 | 0 | 65 |  |
| 21. | Portable Lights | 12 | 0 | 12 |  |
| 22. | Energy Saver 45 W Philips | 20 | 0 | 20 |  |
| 23. | Energy Saver 25 W Philips | 20 | 0 | 20 |  |
| 24. | Bamboos 8’-10’ long (For Lighting arrangements) | 40 | 0 | 40 |  |
| 25. | Petrol for Running Generator | 600 | 0 | 600 |  |
| 26. | Steel Charpoy | 3 | 0 | 3 |  |
| 27. | Folding Table | 1 | 0 | 1 |  |
| 28. | Folding Chair | 3 | 0 | 3 |  |
| 29. | Polyproplyne bags 50 kg capacity | 1500 | 0 | 1500 |  |
| 30. | Hand Saw | 2 | 0 | 2 |  |
| 31. | Wire Rope 1/2" | 150 | 0 | 150 |  |
| 32. | Naylon Rope 3/8" | 50 | 0 | 50 |  |
| 33. | Naylon rope3/4" | 75 | 0 | 75 |  |
| 34. | Naylon Rope 1/4" | 50 | 0 | 50 |  |
| 35. | Umbrellas | 4 | 0 | 4 |  |
| 36. | Rain Coats | 4 | 0 | 4 |  |
| 37. | Water Cooler | 1 | 0 | 1 |  |
| 38. | Water set | 1 | 0 | 1 |  |
| 39. | First Aid Box | 1 | 0 | 1 |  |
| 40. | Lifebuoy | 3 | 0 | 3 |  |

NOTE:-	Balance quantity of flood fighting material will be procured before the start of flood season 2024 and material is stored at camp site.

13.4	DETAIL OF OTHER INFRASTRUCTURE LIKE ELECTRICITY, 	SUI GAS, TELEPHONE INSTALLATION, ROAD NETWORK, 	OTHER BUILDING, CANAL AND DRAINAGE NETWORK.

DETAIL OF IRRIGATION NETWORK ON RIGHT SIDE

| Sr.# | Name of Channel | From RD. | To RD. |
| --- | --- | --- | --- |
| No Irrigation system/ infrastructure exists |  |  |  |

DETAIL OF ROAD NETWORK

| Sr | Name of Village | Population | Detail of Infrastructure |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Boys school | Girl school | Health Centers | Tel: Exchange | Misc: | Road |
| 1 | Ikhlaspur to Kot Naina Road | 20000 | 5 | 4 | 1 | -- | -- | 1 |
| Total |  | 20000 | 5 | 4 | 1 | -- | -- | 1 |

CHAPTER - 13

EMERGENCY CONTINGENCY / PLAN FOR VULNERABLE SITES

PLAN

C

- EMERGENCY CONTINGENCY PLAN FOR VULNERABLE REACH BHECO CHAK FLOOD BUND FROM RD.25+000 TO 29+000.

  - PLAN SHOWING ROUTE OF FLOOD WATER COMING OUT THE BREACH.

3. BhecoChak Flood Bund FROM RD.25+000 TO 29+000.

13.2	DETAIL OF VILLAGE ABADIES LIKELY TO BE AFFECTED 	AND 	THISALSO BE SHOWN ON THE PLAN

Boora Dala, Mundiali, Gole, Ali Lngah, Mundhi khail, Manzoorpura plot, Doda, Kartarpur.

13.3	STRATEGY AND ACTION TAKEN, EXPLAINED IN 	DETAIL. THIS MAYINCLUDE

The necessary repairs of the flood bund works will be carried out before start of flood season. Moreover, arrangements to establish flood camps will be ensured and deficient quantity of flood fighting material and equipment will be procured before time for watching during flood season.

The flood fighting material will be kept in stores which are located in the premises of Stores under the control/ custody of the Sub Engineers concerned.

13.3.1	ARRANGEMENTS.

Flood fighting camp will established at Spur No.4 of Bheco Chak Flood Bund

13.3.2	ESTABLISHMENT OF FLOOD FIGHTING CAMPS

The Flood Fighting camps will be arranged at between RD.25+000 to RD.29+000 of Bheco Chak Flood Bund as per requirements according to flood situation.

13.3.3	DUTIES OF OFFICER / OFFICIALS AND THEIR CAMP SITES

| Sr, No | Flood Situation. | Officer/Officials on duty (Name, Designation, Cell No.) | Camp Location |
| --- | --- | --- | --- |
| 1 | Low Flood | Ahsan Naveed, Sub Divisional officer, 0321-7436970 Mr. M. Ijaz Sub Engineer Jalala Bund, 0335-1613955 Abdul Kareem, Sub Engineer Haji Pur Bund 0301-6332951 Abdul Kareem, Sub Engineer S&I Sec 0301-6332951 M. Ijaz, Sub Engineer Bheco chak Bund, 0335-1613955 | -RD 13+000 -RD 20+000 -Tie Bund -RD 26+000 |
| 2 | Medium Flood | Ahsan Naveed, Sub Divisional officer, 0321-7436970 Mr. M. Ijaz Sub Engineer Jalala Bund, 0335-1613955 Abdul Kareem, Sub Engineer Haji Pur Bund 0301-6332951 Abdul Kareem, Sub Engineer S&I Sec 0301-6332951 M. Ijaz, Sub Engineer Bheco chak Bund, 0335-1613955 | -RD 13+000 -RD 20+000 -Tie Bund -RD 26+000 |
| 3 | High Flood | Ahsan Naveed, Sub Divisional officer, 0321-7436970 Mr. M. Ijaz Sub Engineer Jalala Bund, 0335-1613955 Abdul Kareem, Sub Engineer Haji Pur Bund 0301-6332951 Abdul Kareem, Sub Engineer S&I Sec 0301-6332951 M. Ijaz, Sub Engineer Bheco chak Bund, 0335-1613955 | -RD 13+000 -RD 20+000 -Tie Bund -RD 26+000 |
| 4 | Very High Flood | Ali Raza, Executive Engineer, 0301-1302162 Ahsan Naveed, Sub Divisional officer, 0321-7436970 Mr. M. Ijaz Sub Engineer Jalala Bund, 0335-1613955 Abdul Kareem, Sub Engineer Haji Pur Bund 0301-6332951 Abdul Kareem, Sub Engineer S&I Sec 0301-6332951 M. Ijaz, Sub Engineer Bheco chak Bund, 0335-1613955 | RD 38+000 -RD 20+000 -Tie Bund -RD 26+000 |
| 5 | Exceptionally Flood | Ali Raza, Executive Engineer, 0301-1302162 Ahsan Naveed, Sub Divisional officer, 0321-7436970 Mr. M. Ijaz Sub Engineer Jalala Bund, 0335-1613955 Abdul Kareem, Sub Engineer Haji Pur Bund 0301-6332951 Abdul Kareem, Sub Engineer S&I Sec 0301-6332951 M. Ijaz, Sub Engineer Bheco chak Bund, 0335-1613955 | -RD 38+000 -RD 20+000 -Tie Bund -RD 26+000 |

13.3.4 DEPARTMENTAL MACHINERY AVAILABLE

One number Tractor with hydraulic trolley & Boozer is available.

13.3.5 MACHINERY AVAILABLE FROM PRIVATE SOURCE.

Machinery will be arranged if required from enlisted Government Contractors.

13.3.6 FLOOD FIGHTING MATERIAL REQUIRED.

13.3.7 FLOOD FIGHTING MATERIAL AVAILABLE

| Sr. | Name of Article | Total Quantity Required | Available Quantity | Balance Quantity | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1. | Shouldaris/ Camp tents (Water Proof Good Quality) | 1 | 0 | 1 | The balance quantity will be procured before the onset of the Flood Season 2024 |
| 2. | Camp Tables (Good Quality) | 2 | 0 | 2 |  |
| 3. | Camp Chairs | 12 | 0 | 12 |  |
| 4. | Baskets | 100 | 0 | 100 |  |
| 5. | Empty Gunny Bags (used) | 800 | 0 | 800 |  |
| 6. | Chouldaries. | 1 | 0 | 1 |  |
| 7. | Sutli | 12 | 0 | 12 |  |
| 8. | Needles. | 5 | 0 | 5 |  |
| 9. | Killas | 50 | 0 | 50 |  |
| 10. | Flood Lights | 3 | 0 | 3 |  |
| 11. | Wooden Hamers | 1 | 0 | 1 |  |
| 12. | Kassaies | 50 | 0 | 50 |  |
| 13. | Axes | 4 | 0 | 4 |  |
| 14. | Manila Rope | 100 | 0 | 100 |  |
| 15. | Life Jacket | 6 | 0 | 6 |  |
| 16. | Generator (Mitsubushi Diesel PS .35 Capacity 3-KV | 1 | 0 | 1 |  |
| 17. | Electric Cable 7/0029 | 2 | 0 | 2 |  |
| 18. | Electric Cable 3/0029 | 2 | 0 | 2 |  |
| 19. | Switch | 15 | 0 | 15 |  |
| 20. | Holders | 65 | 0 | 65 |  |
| 21. | Portable Lights | 12 | 0 | 12 |  |
| 22. | Energy Saver 45 W Philips | 20 | 0 | 20 |  |
| 23. | Energy Saver 25 W Philips | 20 | 0 | 20 |  |
| 24. | Bamboos 8’-10’ long (For Lighting arrangements) | 40 | 0 | 40 |  |
| 25. | Petrol for Running Generator | 600 | 0 | 600 |  |
| 26. | Steel Charpoy | 3 | 0 | 3 |  |
| 27. | Folding Table | 1 | 0 | 1 |  |
| 28. | Folding Chair | 3 | 0 | 3 |  |
| 29. | Polyproplyne bags 50 kg capacity | 1500 | 0 | 1500 |  |
| 30. | Hand Saw | 2 | 0 | 2 |  |
| 31. | Wire Rope 1/2" | 150 | 0 | 150 |  |
| 32. | Naylon Rope 3/8" | 50 | 0 | 50 |  |
| 33. | Naylon rope3/4" | 75 | 0 | 75 |  |
| 34. | Naylon Rope 1/4" | 50 | 0 | 50 |  |
| 35. | Umbrellas | 4 | 0 | 4 |  |
| 36. | Rain Coats | 4 | 0 | 4 |  |
| 37. | Water Cooler | 1 | 0 | 1 |  |
| 38. | Water set | 1 | 0 | 1 |  |
| 39. | First Aid Box | 1 | 0 | 1 |  |
| 40. | Lifebuoy | 3 | 0 | 3 |  |

Note:-	Balance quantity of flood fighting material will be procured before the start of flood season 2024 and material is stored at camp site.

13.4	DETAIL OF OTHER INFRASTRUCTURE LIKE ELECTRICITY, 	SUI GAS, TELEPHONE INSTALLATION, ROAD NETWORK, 	OTHER BUILDING, CANAL AND DRAINAGE NETWORK.

DETAIL OF IRRIGATION NETWORK ON RIGHT SIDE

| Sr.# | Name of Channel | From RD. | To RD. |
| --- | --- | --- | --- |
| No Irrigation system/ infrastructure exists |  |  |  |

DETAIL OF ROAD NETWORK

| Sr | Name of Village | Population | Detail of Infrastructure |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Boys school | Girl school | Health Centers | Tel: Exchange | Misc: | Road |
| 1 | Boora Dala | 3000 | 1 | 1 |  | -- | -- | 1 |
| 2 | Mundiali | 2000 | 1 | 1 | -- | -- | -- | 1 |
| 3 | Gole | 3900 | 1 | 1 | -- | -- | -- | 1 |
| 4 | Ali Langah | 500 | - | - | -- | -- | -- | 1 |
| 5 | Mundhi Khel | 2500 | 1 | 1 | 1 | -- |  |  |
| 6 | ManzoorPua Plot | 7000 | 1 | 1 | 1 | -- | U.C | 1 |
| 7 | Kartarpur | 1500 | - | - | -- | -- | Darbar kartarpur sahib | 1 |
| Total |  | 20400 | 5 | 5 | 2 | - |  | 6 |

CHAPTER - 13

EMERGENCY CONTINGENCY / PLAN FOR VULNERABLE SITES

PLAN

D

- EMERGENCY CONTINGENCY PLAN FOR VULNERABLE REACH HAJIPUR GUJRAN BETWEEN SPUR 4 & 5.

  - PLAN SHOWING ROUTE OF FLOOD WATER COMING OUT THE BREACH.

4. HAJIPUR GUJRAN BETWEEN SPUR 4 & 5.

13.2	DETAIL OF VILLAGE ABADIES LIKELY TO BE AFFECTED 	AND 	THISALSO BE SHOWN ON THE PLAN

Daria, Dovaba, Dera Noor Malik, Tatia, Tabba, Chana

13.3	STRATEGY AND ACTION TAKEN, EXPLAINED IN 	DETAIL. THIS MAYINCLUDE

The necessary repairs of the flood bund works will be carried out before start of flood season. Moreover, arrangements to establish flood camps will be ensured and deficient quantity of flood fighting material and equipment will be procured before time for watching during flood season.

The flood fighting material will be kept in stores which are located in the premises of Stores under the control/ custody of the Sub Engineers concerned.

13.3.1	ARRANGEMENTS.

Flood fighting camp will established at Spur No.4 of Bheco Chak Flood Bund

13.3.2	ESTABLISHMENT OF FLOOD FIGHTING CAMPS

The Flood Fighting camps will be arranged at Spur No.4 & 5 of Hajipur Gujran Flood Bund as per requirements according to flood situation.

13.3.3	DUTIES OF OFFICER / OFFICIALS AND THEIR CAMP SITES

| Sr, No | Flood Situation. | Officer/Officials on duty (Name, Designation, Cell No.) | Camp Location |
| --- | --- | --- | --- |
| 1 | Low Flood | Ahsan Naveed, Sub Divisional officer, 0321-7436970 Mr. M. Ijaz Sub Engineer Jalala Bund, 0335-1613955 Abdul Kareem, Sub Engineer Haji Pur Bund 0301-6332951 Abdul Kareem, Sub Engineer S&I Sec 0301-6332951 M. Ijaz, Sub Engineer Bheco chak Bund, 0335-1613955 | -RD 13+000 -RD 20+000 -Tie Bund -RD 26+000 |
| 2 | Medium Flood | Ahsan Naveed, Sub Divisional officer, 0321-7436970 Mr. M. Ijaz Sub Engineer Jalala Bund, 0335-1613955 Abdul Kareem, Sub Engineer Haji Pur Bund 0301-6332951 Abdul Kareem, Sub Engineer S&I Sec 0301-6332951 M. Ijaz, Sub Engineer Bheco chak Bund, 0335-1613955 | -RD 13+000 -RD 20+000 -Tie Bund -RD 26+000 |
| 3 | High Flood | Ahsan Naveed, Sub Divisional officer, 0321-7436970 Mr. M. Ijaz Sub Engineer Jalala Bund, 0335-1613955 Abdul Kareem, Sub Engineer Haji Pur Bund 0301-6332951 Abdul Kareem, Sub Engineer S&I Sec 0301-6332951 M. Ijaz, Sub Engineer Bheco chak Bund, 0335-1613955 | -RD 13+000 -RD 20+000 -Tie Bund -RD 26+000 |
| 4 | Very High Flood | Ali Raza, Executive Engineer, 0301-1302162 Ahsan Naveed, Sub Divisional officer, 0321-7436970 Mr. M. Ijaz Sub Engineer Jalala Bund, 0335-1613955 Abdul Kareem, Sub Engineer Haji Pur Bund 0301-6332951 Abdul Kareem, Sub Engineer S&I Sec 0301-6332951 M. Ijaz, Sub Engineer Bheco chak Bund, 0335-1613955 | RD 38+000 -RD 20+000 -Tie Bund -RD 26+000 |
| 5 | Exceptionally Flood | Ali Raza, Executive Engineer, 0301-1302162 Ahsan Naveed, Sub Divisional officer, 0321-7436970 Mr. M. Ijaz Sub Engineer Jalala Bund, 0335-1613955 Abdul Kareem, Sub Engineer Haji Pur Bund 0301-6332951 Abdul Kareem, Sub Engineer S&I Sec 0301-6332951 M. Ijaz, Sub Engineer Bheco chak Bund, 0335-1613955 | -RD 38+000 -RD 20+000 -Tie Bund -RD 26+000 |

13.3.4 DEPARTMENTAL MACHINERY AVAILABLE

One number Tractor with hydraulic trolley & Boozer is available.

13.3.5 MACHINERY AVAILABLE FROM PRIVATE SOURCE.

Machinery will be arranged if required from enlisted Government Contractors.

13.3.6 FLOOD FIGHTING MATERIAL REQUIRED.

13.3.7 FLOOD FIGHTING MATERIAL AVAILABLE

| Sr. | Name of Article | Total Quantity Required | Available Quantity | Balance Quantity | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1. | Shouldaris/ Camp tents (Water Proof Good Quality) | 1 | 0 | 1 | The balance quantity will be procured before the onset of the Flood Season 2024 |
| 2. | Camp Tables (Good Quality) | 2 | 0 | 2 |  |
| 3. | Camp Chairs | 12 | 0 | 12 |  |
| 4. | Baskets | 100 | 0 | 100 |  |
| 5. | Empty Gunny Bags (used) | 800 | 0 | 800 |  |
| 6. | Chouldaries. | 1 | 0 | 1 |  |
| 7. | Sutli | 12 | 0 | 12 |  |
| 8. | Needles. | 5 | 0 | 5 |  |
| 9. | Killas | 50 | 0 | 50 |  |
| 10. | Flood Lights | 3 | 0 | 3 |  |
| 11. | Wooden Hamers | 1 | 0 | 1 |  |
| 12. | Kassaies | 50 | 0 | 50 |  |
| 13. | Axes | 4 | 0 | 4 |  |
| 14. | Manila Rope | 100 | 0 | 100 |  |
| 15. | Life Jacket | 6 | 0 | 6 |  |
| 16. | Generator (Mitsubushi Diesel PS .35 Capacity 3-KV | 1 | 0 | 1 |  |
| 17. | Electric Cable 7/0029 | 2 | 0 | 2 |  |
| 18. | Electric Cable 3/0029 | 2 | 0 | 2 |  |
| 19. | Switch | 15 | 0 | 15 |  |
| 20. | Holders | 65 | 0 | 65 |  |
| 21. | Portable Lights | 12 | 0 | 12 |  |
| 22. | Energy Saver 45 W Philips | 20 | 0 | 20 |  |
| 23. | Energy Saver 25 W Philips | 20 | 0 | 20 |  |
| 24. | Bamboos 8’-10’ long (For Lighting arrangements) | 40 | 0 | 40 |  |
| 25. | Petrol for Running Generator | 600 | 0 | 600 |  |
| 26. | Steel Charpoy | 3 | 0 | 3 |  |
| 27. | Folding Table | 1 | 0 | 1 |  |
| 28. | Folding Chair | 3 | 0 | 3 |  |
| 29. | Polyproplyne bags 50 kg capacity | 1500 | 0 | 1500 |  |
| 30. | Hand Saw | 2 | 0 | 2 |  |
| 31. | Wire Rope 1/2" | 150 | 0 | 150 |  |
| 32. | Naylon Rope 3/8" | 50 | 0 | 50 |  |
| 33. | Naylon rope3/4" | 75 | 0 | 75 |  |
| 34. | Naylon Rope 1/4" | 50 | 0 | 50 |  |
| 35. | Umbrellas | 4 | 0 | 4 |  |
| 36. | Rain Coats | 4 | 0 | 4 |  |
| 37. | Water Cooler | 1 | 0 | 1 |  |
| 38. | Water set | 1 | 0 | 1 |  |
| 39. | First Aid Box | 1 | 0 | 1 |  |
| 40. | Lifebuoy | 3 | 0 | 3 |  |

Note:-	Balance quantity of flood fighting material will be procured before the start of flood season 2024 and material is stored at camp site.

13.4	DETAIL OF OTHER INFRASTRUCTURE LIKE ELECTRICITY, 	SUI GAS, TELEPHONE INSTALLATION, ROAD NETWORK, 	OTHER BUILDING, CANAL AND DRAINAGE NETWORK.

DETAIL OF IRRIGATION NETWORK ON RIGHT SIDE

| Sr.# | Name of Channel | From RD. | To RD. |
| --- | --- | --- | --- |
| No Irrigation system/ infrastructure exists |  |  |  |

DETAIL OF ROAD NETWORK

| Sr | Name of Village | Population | Detail of Infrastructure |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Boys school | Girl school | Health Centers | Tel: Exchange | Misc: | Road |
| 1 | Kot Nania to Dera Noor Malik | 10000 | 2 | 2 |  | -- | -- | 1 |
| 2 | Jughayal to Tabba | 5000 | 1 | 1 |  |  |  | 1 |
| Total |  | 15000 | 3 | 3 |  | - |  | 2 |

CHAPTER - 13

EMERGENCY CONTINGENCY / PLAN FOR VULNERABLE SITES

PLAN

E

- EMERGENCY CONTINGENCY PLAN FOR VULNERABLE REACH DEG NULLAH RD.16+000 TO RD.17+000/R

13.1  PLAN SHOWING ROUTE OF FLOOD WATER COMING OUT THE BREACH.

5. DEG NULLAH RD RD.16+000 TO RD.17+000/R

13.2	DETAIL OF VILLAGE ABADIES LIKELY TO BE AFFECTED 	AS SHOWN ON THE PLAN

Shahzada, Panelky, Dhaul, Pasrur City, Pasrur Cant, Kotli Syedan, Jaistiwala Down.

13.3	STRATEGY AND ACTION TAKEN, EXPLAINED IN 	DETAIL. THIS MAY	INCLUDE

The necessary repairs of the flood bund works will be carried out before start of flood season. Moreover, arrangements to establish flood camps will be ensured and deficient quantity of flood fighting material and equipment will be procured before time for watching during flood season.

The flood fighting material will be kept in stores which are located in the premises of Stores under the control/ custody of the Sub Engineers concerned.

13.3.1ARRANGEMENTS.

Flood fighting camp will established at Right bank at RD 18+500

13.3.2ESTABLISHMENT OF FLOOD FIGHTING CAMPS

The Flood Fighting camps will be arranged at RD.18+500 of Right bank as per requirements according to flood situation.

13.3.3	DUTIES OF OFFICER / OFFICIALS AND THEIR CAMP SITES

| Sr, No | Flood Situation. | Officer/Officials on duty (Name, Designation, Cell No.) | Camp Location |
| --- | --- | --- | --- |
| 1 | Low Flood | M. Moazzam Ali, Sub Divisional officer, 0300-4975037 M. Arslan, Sub Engineer Chandian, 0301-2979301 M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 | -Dowel Bund -Pejowali Hut |
| 2 | Medium Flood | M. Moazzam Ali, Sub Divisional officer, 0300-4975037 M. Arslan, Sub Engineer Chandian, 0301-2979301 M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 | -Dowel Bund -Pejowali Hut |
| 3 | High Flood | M. Moazzam Ali, Sub Divisional officer, 0300-4975037 M. Arslan, Sub Engineer Chandian, 0301-2979301 M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 Mehmood Ahmad, Sub Engineer Zafarwal, 0300-6978519 | -Dowel Bund -Pejowali Hut -Spur RD 75 |
| 4 | Very High Flood | Ali Raza, Executive Engineer, 0301-1302162 M. Moazzam Ali, Sub Divisional officer, 0300-4975037 M. Arslan, Sub Engineer Chandian, 0301-2979301 M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 Mehmood Ahmad, Sub Engineer Zafarwal, 0300-6978519 | -Dowel Bund -Pejowali Hut -Spur RD 75 |
| 5 | Exceptionally Flood | Ali Raza, Executive Engineer, 0301-1302162 M. Moazzam Ali, Sub Divisional officer, 0300-4975037 M. Arslan, Sub Engineer Chandian, 0301-2979301 M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 Mehmood Ahmad, Sub Engineer Zafarwal, 0300-6978519 | -Dowel Bund -Pejowali Hut -Spur RD 75 |

13.3.4 DEPARTMENTAL MACHINERY AVAILABLE

One number Tractor with hydraulic trolley & Boozer is available.

13.3.5 MACHINERY AVAILABLE FROM PRIVATE SOURCE.

Machinery will be arranged if required from enlisted Government Contractors.

13.3.6 FLOOD FIGHTING MATERIAL REQUIRED.

13.3.7 FLOOD FIGHTING MATERIAL AVAILABLE.

| Sr. | Name of Article | Total Quantity Required | Available Quantity | Balance Quantity | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1. | Shouldaris/ Camp tents (Water Proof Good Quality) | 1 | 0 | 1 | The balance quantity will be procured before the onset of the Flood Season 2024 |
| 2. | Camp Tables (Good Quality) | 2 | 0 | 2 |  |
| 3. | Camp Chairs | 12 | 0 | 12 |  |
| 4. | Baskets | 46 | 0 | 46 |  |
| 5. | Empty Gunny Bags (used) | 633 | 0 | 633 |  |
| 6. | Swiss Cottage Tent | 1 | 0 | 1 |  |
| 7. | Sutli | 3 | 0 | 3 |  |
| 8. | Needles. | 3 | 0 | 3 |  |
| 9. | Killas | 20 | 0 | 20 |  |
| 10. | Flood Lights | 1 | 0 | 1 |  |
| 11. | Wooden Hamers | 1 | 0 | 1 |  |
| 12. | Kassaies | 20 | 0 | 20 |  |
| 13. | Axes | 2 | 0 | 2 |  |
| 14. | Manila Rope | 50 | 0 | 50 |  |
| 15. | Life Jacket | 2 | 0 | 2 |  |
| 16. | Generator (Capacity 3-KVA) | 1 | 0 | 1 |  |
| 17. | Electric Cable 7/0029 | 2 | 0 | 2 |  |
| 18. | Electric Cable 3/0029 | 2 | 0 | 2 |  |
| 19. | Switch | 15 | 0 | 15 |  |
| 20. | Holders | 25 | 0 | 25 |  |
| 21. | Portable Lights | 15 | 0 | 15 |  |
| 22. | Energy Saver 45 W Philips | 20 | 0 | 20 |  |
| 23. | Energy Saver 25 W Philips | 20 | 0 | 20 |  |
| 24. | Bamboos 8’-10’ long (For Lighting arrangements) | 50 | 0 | 50 |  |
| 25. | Petrol for Running Generator | 400 Ltr | 0 | 400 Ltr |  |
| 26. | Steel Charpoy | 3 | 0 | 3 |  |
| 27. | Folding Table | 1 | 0 | 1 |  |
| 28. | Folding Chair | 2 | 0 | 2 |  |
| 29. | Polyproplyne bags 50 kg capacity | 1000 | 0 | 1000 |  |
| 30. | Hand Saw | 1 | 0 | 1 |  |
| 31. | Wire Rope 1/2" | 50 | 0 | 50 |  |
| 32. | Naylon Rope 3/8" | 20 | 0 | 20 |  |
| 33. | Naylon rope3/4" | 20 | 0 | 20 |  |
| 34. | Naylon Rope 1/4" | 20 | 0 | 20 |  |
| 35. | Umbrellas | 2 | 0 | 2 |  |
| 36. | Rain Coats | 2 | 0 | 2 |  |
| 37. | Water Cooler | 1 | 0 | 1 |  |
| 38. | Water set | 1 | 0 | 1 |  |
| 39. | First Aid Box | 1 | 0 | 1 |  |
| 40. | Lifebuoy | 2 | 0 | 2 |  |

Note:-Balance quantity of flood fighting material will be procured before the start of flood season 2024 and material is stored at camp site.

13.4	DETAIL OF OTHER INFRASTRUCTURE LIKE ELECTRICITY, 	SUI GAS, TELEPHONE INSTALLATION, ROAD NETWORK, 	OTHER BUILDING, CANAL AND DRAINAGE NETWORK.

DETAIL OF IRRIGATION NETWORK ON RIGHT SIDE

| Sr.# | Name of Channel | From RD. | To RD. |
| --- | --- | --- | --- |
| No Irrigation system/ infrastructure exists |  |  |  |

DETAIL OF ROAD NETWORK

| Sr | Name of Village | Population | Detail of Infrastructure |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Boys school | Girl school | Health Centers | Tel: Exchange | Misc: | Road |
| 1 | Shahzada | 1500 | 1 | 1 | 1 | -- | -- | 1 |
| 2 | Panelky | 800 | 1 | 1 | -- | -- | -- | -- |
| 3 | Dhaul | 600 | -- | -- | -- | -- | -- | -- |
| 4 | Pasrur city | 82485 | 3 | 3 | 2 | 2 | -- | 3 |
| 5 | Pasrur cant | 4000 | 1 | 1 | -- | 1 | -- | 2 |
| 6 | Kotli Syedan | 700 | 1 | 1 | 1 | -- | -- | 1 |
| 7 | Jastiwala Down | 300 | -- | -- | -- | -- | -- | -- |
| Total |  | 90385 | 7 | 7 | 4 | 3 | - | 7 |

Note:-

These villages fall in District Sialkot as well as canal network does not exist.

CHAPTER - 13

EMERGENCY CONTINGENCY / PLAN FOR VULNERABLE SITES

PLAN

F

- EMERGENCY CONTINGENCY PLAN FOR VULNERABLE REACH DEG NULLAH RD.17+000 TO RD.18+000/L

13.1  PLAN SHOWING ROUTE OF FLOOD WATER COMING OUT THE BREACH.

6. DEG NULLAH RD RD.17+000 TO RD.18+000/L

13.2	DETAIL OF VILLAGE ABADIES LIKELY TO BE AFFECTED 	AS SHOWN ON THE PLAN

Jastiwala, Bagh, Kamely Bagh, Qila Ahmed Abad

13.3	STRATEGY AND ACTION TAKEN, EXPLAINED IN 	DETAIL. THIS MAY	INCLUDE

The necessary repairs of the flood bund works will be carried out before start of flood season. Moreover, arrangements to establish flood camps will be ensured and deficient quantity of flood fighting material and equipment will be procured before time for watching during flood season.

The flood fighting material will be kept in stores which are located in the premises of Stores under the control/ custody of the Sub Engineers concerned.

13.3.1ARRANGEMENTS.

Flood fighting camp will established at Left bank at RD 20+000

13.3.2  ESTABLISHMENT OF FLOOD FIGHTING CAMPS

The Flood Fighting camps will be arranged at RD.20+000 of Left bank as per requirements according to flood situation.

13.3.3	DUTIES OF OFFICER / OFFICIALS AND THEIR CAMP SITES

| Sr, No | Flood Situation. | Officer/Officials on duty (Name, Designation, Cell No.) | Camp Location |
| --- | --- | --- | --- |
| 1 | Low Flood | M. Moazzam Ali, Sub Divisional officer, 0300-4975037 M. Arslan, Sub Engineer Chandian, 0301-2979301 M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 | -Dowel Bund -Pejowali Hut |
| 2 | Medium Flood | M. Moazzam Ali, Sub Divisional officer, 0300-4975037 M. Arslan, Sub Engineer Chandian, 0301-2979301 M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 | -Dowel Bund -Pejowali Hut |
| 3 | High Flood | M. Moazzam Ali, Sub Divisional officer, 0300-4975037 M. Arslan, Sub Engineer Chandian, 0301-2979301 M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 Mehmood Ahmad, Sub Engineer Zafarwal, 0300-6978519 | -Dowel Bund -Pejowali Hut -Spur RD 75 |
| 4 | Very High Flood | Ali Raza, Executive Engineer, 0301-1302162 M. Moazzam Ali, Sub Divisional officer, 0300-4975037 M. Arslan, Sub Engineer Chandian, 0301-2979301 M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 Mehmood Ahmad, Sub Engineer Zafarwal, 0300-6978519 | -Dowel Bund -Pejowali Hut -Spur RD 75 |
| 5 | Exceptionally Flood | Ali Raza, Executive Engineer, 0301-1302162 M. Moazzam Ali, Sub Divisional officer, 0300-4975037 M. Arslan, Sub Engineer Chandian, 0301-2979301 M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 Mehmood Ahmad, Sub Engineer Zafarwal, 0300-6978519 | -Dowel Bund -Pejowali Hut -Spur RD 75 |

13.3.4 DEPARTMENTAL MACHINERY AVAILABLE

One number Tractor with hydraulic trolley & Boozer is available.

13.3.5 MACHINERY AVAILABLE FROM PRIVATE SOURCE.

Machinery will be arranged if required from enlisted Government Contractors.

13.3.6 FLOOD FIGHTING MATERIAL REQUIRED.

13.3.7 FLOOD FIGHTING MATERIAL AVAILABLE.

| Sr. | Name of Article | Total Quantity Required | Available Quantity | Balance Quantity | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1. | Shouldaris/ Camp tents (Water Proof Good Quality) | 1 | 0 | 1 | The balance quantity will be procured before the onset of the Flood Season 2024 |
| 2. | Camp Tables (Good Quality) | 2 | 0 | 2 |  |
| 3. | Camp Chairs | 12 | 0 | 12 |  |
| 4. | Baskets | 46 | 0 | 46 |  |
| 5. | Empty Gunny Bags (used) | 633 | 0 | 633 |  |
| 6. | Swiss Cottage Tent | 1 | 0 | 1 |  |
| 7. | Sutli | 3 | 0 | 3 |  |
| 8. | Needles. | 3 | 0 | 3 |  |
| 9. | Killas | 20 | 0 | 20 |  |
| 10. | Flood Lights | 1 | 0 | 1 |  |
| 11. | Wooden Hamers | 1 | 0 | 1 |  |
| 12. | Kassaies | 20 | 0 | 20 |  |
| 13. | Axes | 2 | 0 | 2 |  |
| 14. | Manila Rope | 50 | 0 | 50 |  |
| 15. | Life Jacket | 2 | 0 | 2 |  |
| 16. | Generator (Capacity 3-KVA) | 1 | 0 | 1 |  |
| 17. | Electric Cable 7/0029 | 2 | 0 | 2 |  |
| 18. | Electric Cable 3/0029 | 2 | 0 | 2 |  |
| 19. | Switch | 15 | 0 | 15 |  |
| 20. | Holders | 25 | 0 | 25 |  |
| 21. | Portable Lights | 15 | 0 | 15 |  |
| 22. | Energy Saver 45 W Philips | 20 | 0 | 20 |  |
| 23. | Energy Saver 25 W Philips | 20 | 0 | 20 |  |
| 24. | Bamboos 8’-10’ long (For Lighting arrangements) | 50 | 0 | 50 |  |
| 25. | Petrol for Running Generator | 400 Ltr | 0 | 400 Ltr |  |
| 26. | Steel Charpoy | 3 | 0 | 3 |  |
| 27. | Folding Table | 1 | 0 | 1 |  |
| 28. | Folding Chair | 2 | 0 | 2 |  |
| 29. | Polyproplyne bags 50 kg capacity | 1000 | 0 | 1000 |  |
| 30. | Hand Saw | 1 | 0 | 1 |  |
| 31. | Wire Rope 1/2" | 50 | 0 | 50 |  |
| 32. | Naylon Rope 3/8" | 20 | 0 | 20 |  |
| 33. | Naylon rope3/4" | 20 | 0 | 20 |  |
| 34. | Naylon Rope 1/4" | 20 | 0 | 20 |  |
| 35. | Umbrellas | 2 | 0 | 2 |  |
| 36. | Rain Coats | 2 | 0 | 2 |  |
| 37. | Water Cooler | 1 | 0 | 1 |  |
| 38. | Water set | 1 | 0 | 1 |  |
| 39. | First Aid Box | 1 | 0 | 1 |  |
| 40. | Lifebuoy | 2 | 0 | 2 |  |

Note:- Balance quantity of flood fighting material will be procured before the start of flood season 2024 and material is stored at camp site.

13.4	DETAIL OF OTHER INFRASTRUCTURE LIKE ELECTRICITY, 	SUI GAS, TELEPHONE INSTALLATION, ROAD NETWORK, 	OTHER BUILDING, CANAL AND DRAINAGE NETWORK.

DETAIL OF IRRIGATION NETWORK ON RIGHT SIDE

| Sr.# | Name of Channel | From RD. | To RD. |
| --- | --- | --- | --- |
| No Irrigation system/ infrastructure exists |  |  |  |

DETAIL OF ROAD NETWORK

| Sr | Name of Village | Population | Detail of Infrastructure |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Boys school | Girl school | Health Centers | Tel: Exchange | Misc: | Road |
| 1 | Jastiwala, , , | 2400 | 1 | 1 |  | -- | -- | 1 |
| 2 | Bagh | 1500 | 1 | 1 | 1 | -- | -- | 1 |
| 3 | Kamely Bagh | 1900 | 1 | 1 | -- | -- | -- | 1 |
| 4 | Qila Ahmed Abad | 8000 | 1 | 1 | 1 | 1 | Union Council | 1 |
| Total |  | 13800 | 4 | 4 | 5 | 1 | 2 | 4 |

Note:-

These villages fall in District Narowal as well as canal network  does not exist.

CHAPTER - 14

ACTION PLAN

14.1	RE-SHUFFLING / RECOUPING PLAN OF RESERVE STOCK OF STONE DEPARTMENTALLY.

If any critical situation during flood season 2023 arises then the requisite quantity of stone as per necessity will be shifted accordingly from one structure / site to another site.

14.2	DETAIL OF INLET AND OUTLET CROSSING ALONGWITH 	CLOSING METHODOLOGY.

No inlet & outlet exist in flood embankments.

14.3	DEPLOYMENT OF MACHINERY (Medium to High Flood).

| Name of Structure | Length in Mile | Vulnerable Reach | Camp Location | Site In-charge by name & Cell No. | Machinery Deployed |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Excavator | Dozer | Trolleys / Dumpers | Tractor with front blade | Labour (Beldar + Mate) | Availability of Stone |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| Bheco Chak Flood Bund from RD.0+000 to RD.30+500 | 5.77 | RD.25+000 to RD.29+000 | Bheco Chak Flood Protection Bund At RD 22+000 | SBE Muhammad Ijaz Mob#0312-7931347 | 3 | - | 8 | 3 | 20+2 | The Stone is available at adjoining bund hajipur Gujran Flood Bund according to sanction reserve stock of stone limit. |
| Jalala Flood Bund from RD.0+000 to RD.26+700 | 5.06 | RD.13+000 to RD.18+000 | Jalala Flood Bund at RD.13+000 | SBE Muhammad Ijaz Mob#0312-7931347 | 1 | - | 3 | 1 | 20+2 |  |
| Deg Nullah RD 0+000 to RD 50+000 | 18.93 | RD 20+000 to RD 38+00 | 02 At Rd 20+000 (L/S & R/S) (Vill. Jastiwala) | M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 | 4 | - | 8 | 4 | 20+2 |  |
| Chandian Dowel Bund RD 0+000 -10+500 | 2.10 | RD 10+500 | At RD 10+000 | SBE Muhamaad Arslam Cell No 0301-2979301 | 1 | - | 4 | 2 | 10+1 | Sufficient stone as per approved limit is available at site |
| Total | 21.88 |  |  |  | 9 | -- | 23 | 10 | 70+7 |  |

Note:- Payment for machinery & work charge employees subject to verification by TPM / Departmental Committee.

14.4 	DEPLOYMENT OF MACHINERY (High to Very High Flood).

| Name of Structure | Length in Mile | Vulnerable Reach | Camp Location | Site In-charge by name & Cell No. | Machinery Deployed |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Excavator | Dozer | Trolleys / Dumpers | Tractor with front blade | Labour (Beldar + Mate) | Availability of Stone |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| Bheco Chak Flood Protection Bund Spur No.3 at RD.13+000. | 0.85 | RD. 3+800 to RD.4+500 | Bheco Chak Flood Protection Bund At RD 22+000 | SBE Muhammad Ijaz Mob#0312-7931347 | 4 | - | 12 | 5 | 30+3 | The Stone is available at adjoining bund hajipur Gujran Flood Bund in sufficient quantity. |
| Jalala Flood Bund from RD.0+000 to RD.26+700 | 5.06 | RD.13+000 to RD.18+000 | Jalala Flood Bund at RD.13+000 | SBE Muhammad Ijaz Mob#0312-7931347 | 2 | - | 6 | 2 | 30+3 |  |
| Deg Nullah RD 0+000 to RD 50+000 | 18.93 | RD 20+000 to RD 38+00 | 02 At Rd 20+000 (L/S & R/S) (Vill. Jastiwala) | M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 | 6 | - | 12 | 6 | 30+3 |  |
| Chandian Dowel Bund RD 0+000 -10+500 | 2.10 | RD 10+500 | At RD 10+000 | SBE Muhamaad Arslam Cell No 0301-2979301 | 2 | - | 8 | 4 | 20+1 | Sufficient stone as per approved limit is available at site |
| Total | 21.88 |  |  |  | 14 | -- | 38 | 17 | 110+10 |  |

Note:- Payment for machinery & work charge employees subject to verification by TPM / Departmental Committee.

14.5 DEPLOYMENT OF MACHINERY (High to ExceptionallyHigh Flood).

| Name of Structure | Length in Mile | Vulnerable Reach | Camp Location | Site In-charge by name & Cell No. | Machinery Deployed |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Excavator | Dozer | Trolleys / Dumpers | Tractor with front blade | Labour (Beldar + Mate) | Availability of Stone |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| Bheco Chak Flood Protection Bund Spur No.3 at RD.13+000. | 0.85 | RD.3+800 to RD.4+500 | Bheco Chak Flood Protection Bund At RD 22+000 | SBE Muhammad Ijaz Mob#0312-7931347 | 6 | 1 | 16 | 12 | 40+4 | The Stone is available at adjoining bund hajipur Gujran Flood Bund in sufficient quantity. |
| Jalala Flood Bund from RD.0+000 to RD.26+700 | 5.06 | RD.13+000 to RD.18+000 | Jalala Flood Bund at RD.13+000 | SBE Muhammad Ijaz Mob#0312-7931347 | 4 | - | 12 | 4 | 40+4 |  |
| Deg Nullah RD 0+000 to RD 50+000 | 18.93 | RD 20+000 to RD 38+00 | 02 At Rd 20+000 (L/S & R/S) (Vill. Jastiwala) | M. Afzal Khan, Sub Engineer Rayya, 0300-7766587 | 8 | 1 | 16 | 12 | 40+4 |  |
| Chandian Dowel Bund RD 0+000 -10+500 | 2.10 | RD 10+500 | At RD 10+000 | SBE Muhamaad Arslam Cell No 0301-2979301 | 4 | - | 8 | 6 | 40+4 | Sufficient stone as per approved limit is available atsite |
| Total | 21.88 |  |  |  | 22 | 2 | 52 | 34 | 160+16 |  |

Note:- Payment for machinery & work charge employees subject to verification by TPM / Departmental Committee.

LIST OF LOCAL CONTRACTORS

| Name of Govt. Contractor | Contact Number | Remarks |
| --- | --- | --- |
| Mohammad Umer Amjad R/O village Sodian | 0304-9183241 | Excavators and other machinery may be made available through contractors. |
| M. Sarwar Babar R/O Head Marala | 0346-6664838 | Excavators and other machinery may be made available through contractors. |

14.6	POLICE DEPLOYMENT PLAN

Proforma – 1

| Sr. | Site of Breaching Section | Concerned Canal Division | Concerned Police Station and District | Police Persons Deployed |  | Remarks (if any) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Inspector / Sub Inspector / A.S.I | Constable |  |
| Not Applicable |  |  |  |  |  |  |

Proforma – 2

| Sr. | Vulnerable sites used for illegal cuts during floods | Concerned Canal Division | Concerned Police Station and District | Police Persons Deployed |  | Remarks (if any) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Inspector / Sub Inspector / A.S.I | Constable |  |
| 1 | Jalala Bund RD 13+00 to 18+000 | Narowal | Kot Nainan Police Station Distt: Narowal | ASI=1 | 2 | -- |
| 2 | Chandian dowel Bund RD 2+00 to 4+000 | Narowal | Saddar Police Station Narowal Distt: Narowal | ASI=1 | 2 | -- |
| 3 | Deg Nullah RD 0+000 to RD 0+000/R | Narowal | Saddar Police Station Pasrur Distt: Sialkot | ASI=1 | 4 | -- |
| 4 | Deg Nullah RD 0+000 to RD 50+000/L | Narowal | Qila Ahmadabad Police Station Distt: Narowal | ASI=1 | 4 | -- |

Proforma – 3

| Sr. | Name of Barrage | Concerned Canal Division | Concerned Police Station and District | Police Persons Deployed |  | Remarks (if any) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Inspector / Sub Inspector / A.S.I | Constable |  |
| Not Applicable |  |  |  |  |  |  |

14.7.DETAIL OF SYNTHETIC BAGS WITH CAPACITY OF 500 KG AND 1000 KG.

| Sr. | Synthetic Bags | Quantity Required | Available Quantity | Balance Quantity | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1. | Capacity 500 KG | 500 No. | -- | 500 No. | Will be procured before onset of Flood Season 2024 |
| 2. | Capacity 1000 KG | 100 No. | -- | 100 No. |  |

14.8	DETAIL OF POLYTHENE SHEETS OF BLACK COLOUR TO PROTECT UPSTREAM SLOPE AGAINST WAVE ACTION AND TO CONTROL SEEPAGE THROUGH EMBANKMENT.

| Sr. | Polythene Sheet | Quantity Required | Available Quantity | Balance Quantity | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1. | Average 20 ft width | 10000 Rft | -- | 10000 Rft. | Will be procured before onset of Flood Season 2024 |

CHAPTER - 15

BACK UP DIVISIONS

(IN CASE OF BREACH)

In case of emergency, Pasrur Link Division of Link Circle will be back-up division for River Ravi and Deg Nullah.

Executive Engineer,

Flood Bund Division,

Narowal.

Superintending Engineer,

Link Circle,

Lahore

Chief Engineer

Irrigation Lahore Zone,

Lahore